# A. COVER SHEET

## Proposed Project Title:

## Application of artificial intelligence in personalized therapy and effectiveness assessment of developmental language and speech sound disorders in children aged 3-6.

Principal Investigator (PI): Associate Professor Quan Thanh Tho

## Awardee Organization Information:

Organization Name: Ho Chi Minh City University of Technology - Vietnam National University Ho Chi Minh City

Address: 268 Ly Thuong Kiet, Ward 14, District 10, Ho Chi Minh City

## Budget and Duration

4.621.460.000 VND for 36 months

## Place of Performance

Ho Chi Minh City, Vietnam

## Senior/Key Personnel

| Name | Organization | Role |
| --- | --- | --- |
| Quan Thanh Tho | University of Technology - VNU-HCM | Principal Investigator (PI) |
| Trinh Huu Tung | Children's Hospital 2, HCMC | Senior Members |
| Pham Hoang Anh | University of Technology - VNU-HCM | Senior Members |
| Le Trong Nhan | University of Technology - VNU-HCM | Senior Members |
| Le Thanh Van | University of Technology - VNU-HCM | Senior Members |
| Ha Thi Thanh Huong | International University - VNU-HCM | Senior Members |
| Ngo Thi Lua | International University - VNU-HCM | Senior Members |
| Huynh Kim Phat | North Carolina A&T State University, USA | Senior Members |
| Nguyen Thanh Sang | Children's Hospital 2, HCMC | Senior Members |
| Nguyen Chau Tuyet Nhu | Children's Hospital 2, HCMC | Member |
| Nguyen Quang Duc | University of Technology - VNU-HCM | Member |
| Vu Nguyen Minh Duc | International University - VNU-HCM | Member |
| Nguyen Thi Dieu Linh | Children's Hospital 2, HCMC | Member |
| Nguyen Ngoc Tuong Vy | Children's Hospital 2, HCMC | Member |

# B. PROJECT SUMMARY

This project addresses the growing prevalence of children’s developmental language and speech sound disorders by leveraging artificial intelligence to support the assessment process and personalized therapy.

Recent estimates suggest that approximately 20% of children in Vietnam are affected by these disorders. Current therapeutic approaches require direct interaction between children and therapists, while at-home practice is often considered supplementary and has limited impact on treatment outcomes. Compounding this challenge is the severe shortage of speech-language pathologists, with fewer than 100 specialists per 100 million people in Vietnam, leading to high workloads for therapists and limited access to care. These factors underscore the urgent need for scalable, technology-driven solutions to mitigate the current constraints in speech and language therapy. To address these challenges, this project proposes an AI-powered system containing a dedicated AI proxy device, computer-based software, and a mobile application. This system is designed to support clinicians in assessing and treating children with developmental language disorders by providing personalized therapy plans, enabling effective at-home practice, and continuously monitoring progress. By reducing the burden on specialists and improving accessibility to care, particularly in underserved areas, this solution has the potential for broad deployment across Vietnam, with an initial focus on hospitals in Ho Chi Minh City, where a higher concentration of patients facilitates early implementation and evaluation.

The intellectual merit of this project lies in its novel application of AI techniques to enhance speech and language therapy. Specifically, the project aims to develop AI models capable of simulating speech and language patterns of children with developmental disorders, analyzing their responses, and generating personalized treatment recommendations. The system will employ real-time adaptation based on individual progress, offering a transformative approach to diagnosis and therapy. Additionally, the AI proxy device, designed to operate modern AI models efficiently, will connect with therapists’ computers to provide real-time analysis and treatment recommendations. To support this, we will also develop dedicated computer-based software that integrates with the AI proxy device, assisting therapists in evaluating disorder severity and generating personalized intervention strategies. Complementing this, a mobile application will leverage AI to deliver therapist-guided, personalized exercises for at-home practice, ensuring continuity of care beyond clinical settings.

The broader impacts of this project are substantial and multifaceted. First, it improves access to speech and language therapy, making it suitable for rural areas and adaptable to different Vietnamese dialects when trained with more diverse Vietnamese language data. Second, the project can create a new therapy paradigm by integrating AI-driven tools that not only enhance the efficiency and effectiveness of treatment but redefine therapeutic approaches, allowing clinicians to focus on complex cases while automating routine tasks. Third, the adaptability of the AI-powered system extends beyond speech and language therapy, with potential applications in other fields requiring structured exercises, such as physical therapy or education, like language learning. Finally, by creating a scalable and adaptable solution, the project can serve as a model for other countries facing similar challenges, contributing to global efforts to improve pediatric healthcare outcomes.

# C. PROJECT DESCRIPTION

## 1. Specific Aims

This project aims to develop an AI-driven system that enhances speech and language therapy for children with developmental language disorders through assessment, personalized treatment, and progress tracking. Our approach consists of three key components:

- AI Proxy Device & Clinician Software: We will develop a hardware-assisted AI proxy device that runs AI models locally to assist clinicians in evaluating speech and language disorders. This system will be integrated with computer-based software to simulate children’s speech patterns, provide data-driven assessments, and personalize treatment recommendations.

- Mobile Application for Children: To extend therapy beyond clinical settings, we will design a mobile application that delivers AI-driven, personalized exercises tailored to each child’s unique speech and language challenges. This app will monitor children’s practice sessions, track their progress, and dynamically adjust exercises to match their evolving needs.

- Digitalized Therapy Management: By integrating AI into both assessment and treatment, we aim to streamline clinicians’ workflows, enable precise progress tracking, and optimize treatment regimens over time. The system will facilitate real-time updates to therapy plans, ensuring that interventions remain effective and adaptable to each child’s development.

## 2. Background and Significance

Development of language and speech in children: Language development is a complex process shaped by biological, cognitive, and environmental factors [54]. By 10–12 months, children typically begin recognizing phonemes of their native language, saying first words, and using meaningful gestures like pointing. Around 18 months, their vocabulary may reach 50 words, with frequent gesture-vocalization combinations. Between 20 and 20–24 months, after acquiring about 100 words, children experience a “vocabulary spurt” and begin forming two-word sentences [54]. By 36 months, with a richer vocabulary, they start producing grammatically complex sentences and can communicate with people outside their family. However, about 11–18% of toddlers aged 18–36 months show delayed lexical development and are referred to as “late talkers,” despite having no neurological, intellectual, or hearing impairments. These delays can affect both expressive and receptive language. While many late talkers improve significantly after age 3 and function within typical language bounds, some may continue to face challenges in daily communication [55].

Developmental language disorder: While many late talkers improve after age three, a subset continues to struggle and may be diagnosed with Developmental Language Disorder (DLD) [55]. According to the CATALISE Consensus, DLD refers to language impairments that arise developmentally and are not caused by biomedical conditions such as brain injury, neurodegenerative diseases, cerebral palsy, or genetic syndromes [56]. The consensus expands diagnostic criteria to include children with significant language impairments regardless of risk factors, co-occurring conditions, or nonverbal IQ [56]. In the UK, DLD affects about 7.6% of children aged 4–5, higher than the prevalence of Autism Spectrum Disorder (1.76%) [58] and ADHD (5%) [59]. Children with DLD often face serious challenges, particularly in preschool and early primary school. For 40–50%, language difficulties also affect thinking and learning processes [68], becoming more apparent as they begin learning to read and write by connecting sounds to letters [69]. DLD also increases the risk, about five times, of facing additional difficulties such as academic struggles, behavioral or mental health issues, emotional regulation problems, and social challenges [68].

Speech sound disorder: Speech sound disorder (SSD) refers to difficulties with producing speech sounds, typically due to two main issues. One is articulation deficits, which are motor-based problems where the child’s mouth, tongue, or lips do not move correctly to produce certain sounds [60, 61]. The other is phonological deficits, which are knowledge-based issues involving difficulty understanding and using the sound rules of a language. In such cases, the child may produce sounds correctly in isolation but misuse them in words according to predictable patterns [60, 61]. SSD differs from language impairments like DLD as it specifically concerns speech sounds [60]. It is one of the most common communication disorders in children, affecting about 8–9% of preschoolers and 2–3% of school-aged children [61]. It is more prevalent in boys and in groups such as children with ear infections or language delays [61, 62]. SSD can seriously impact communication, academic performance, and social-emotional well-being, lowering quality of life [63]. Academic struggles are common, especially in reading and writing, and are more severe when SSD co-occurs with DLD, as children may struggle to follow classroom instructions [63].

Assessment for language and speech sound disorders in children:

For developmental language disorder: There are three main types of assessment. Norm-referenced assessments (standardized tests) compare a child's abilities to those of a representative peer group, offering a snapshot of performance at a given time. These are primarily used to identify potential language impairments [64, 65]. Criterion-referenced assessments evaluate a child's performance against specific skill benchmarks rather than peer comparisons. They help determine what a child can or cannot do, establish intervention targets, and monitor therapy progress over time [64, 65]. Dynamic assessment (DA) focuses on learning potential through a test-teach-retest model. After an initial test, the clinician provides targeted instruction, then retests to assess how well the child learns from the intervention. DA is especially useful for culturally diverse populations and helps distinguish true language impairments from limited exposure or other factors [64].

For Speech sound disorder: For children with SSD, a full speech sound assessment is time-consuming, so the process often begins with a quick screening to identify those who may need further evaluation [66, 67]. There are two types: informal screening, which involves tasks like conversation or reading simple sentences, judged by the examiner; and formal screening, which uses standardized tools with set procedures, often comparing results to age norms or cutoffs [66]. While screening is efficient, it does not provide a diagnosis or determine therapy needs. A comprehensive assessment offers deeper insight and includes [66, 67]: connected speech sampling (speech during conversation/storytelling), single-word testing (using picture-naming to assess specific sounds), error analysis (to detect phonological patterns), stimulability testing (checking if a child can produce sounds correctly with a model), severity and intelligibility ratings (judging speech impact and clarity), and speech perception testing (assessing ability to distinguish similar sounds).

Traditional intervention:

For developmental language disorder: The interventions for children with DLD aged 3 - 5 years aim to enhance expressive and receptive language, promote effective social communication, and build foundational literacy skills [65]. Although typical milestones guide potential goals, the range is extensive. Therefore, clinicians must carefully prioritize targets, balancing developmental sequences with individual factors like the child’s profile, age, severity, and family priorities for focused and relevant therapy [65].

For speech sound disorder: The main goal of SSD treatment is to help individuals produce sounds correctly and use them automatically in everyday speech [67]. The general treatment steps for this disorder include establishment (teaching children how to produce the target sound correctly), generalization (helping them use the sound correctly in sentences or conversation), and maintenance (making the correct production consistent and automatic) [67]. The therapist will select initial sounds or patterns to treat based on different factors: developmental, intelligibility, complexity, stimulability, and client-specific [67].

Technical Background:

Why personalized therapy?: As mentioned above, current therapy for children with language and speech sound disorders primarily relies on direct, in-person sessions with trained therapists. The frequency of these sessions varies depending on the severity of the disorder but typically involves at least 1–2 sessions per week because the daily intervention schedule does not suit typical speech-language pathology practices, and dividing up sessions across weeks is more beneficial than scheduling them all in one week [70]. However, due to a shortage of qualified therapists, many are overwhelmed with high caseloads and unable to provide thorough, individualized care for every child. Digital and personalized therapy presents a promising solution to this challenge. Initial efforts to bring computer-assisted approaches to personalized therapy began as early as 2008 [3–6], but limited technological capabilities stalled progress, creating a need for a new wave of AI-enabled approaches to revitalize the field.

Current technical solutions: A key limitation in developing personalized therapy systems is the challenge of accurately analyzing complex speech symptoms and simulating disorder progression to guide treatment planning [17, 18]. With recent breakthroughs in artificial intelligence, particularly the rise of large language models, personalized medicine has gained renewed attention as a transformative research direction [7, 8]. Language and speech sound disorders are no exception, with a growing number of AI-driven applications aimed at helping children improve their communication skills [9]. However, most existing tools function as standalone solutions without the involvement of a real therapist, which limits their effectiveness [9]. Our proposed approach (detailed in the following section) introduces a novel therapy paradigm. It includes simulated disorder profiling by a multimodal large language model, adaptive assessment, personalized long-term intervention planning, and AI-edge deployment.

Language model usage in education: Evidence from the education domain reinforces the feasibility of this approach, demonstrating how LLMs can effectively simulate learner behavior to support teaching and evaluation.  Monforte et al. [12], for instance, developed a peer agent that generated realistic collaborative interactions, while other studies showed how LLMs can simulate student responses at varying skill levels to evaluate educational content [13–16]. These findings suggest that LLMs are capable not only of modeling diverse learner behaviors but also of providing tailored, pedagogically relevant interactions.

Language model usage in healthcare: In the healthcare domain, LLM-based systems have been used to support history-taking and clinical decision-making training by emulating patient responses and providing structured feedback. Recent studies demonstrate that AI-generated feedback can align with expert human evaluations and enhance clinical reasoning skills in students [17–19]. Moreover, recent work highlights the potential for using LLMs to simulate diverse patient demographics, making medical education more inclusive and accessible [20–22]. Mental health tools like VirtuAlz [23] and PATIENT-𝜓 [24] further show how cognitive behavior models can be integrated into AI simulations, offering a compelling foundation for adapting similar techniques to pediatric speech-language therapy contexts. Although LLMs have been widely studied in the medical domain, their practical deployment demands careful consideration. The deployed system must be evaluated rigorously to ensure safety, fairness, and transparency. [25] emphasize the lack of standardized evaluations, while others raise concerns about algorithmic bias, privacy, and ethical risks of anthropomorphizing AI agents, especially in contexts involving vulnerable populations like children [26, 27].

Adaptive learning and assessment: Central to delivering effective AI-assisted therapy is the ability to assess learners adaptively over time. Adaptive assessment, widely used in education and healthcare, allows for efficient and personalized evaluation or personalized medicine through intelligent item selection [33, 36]. Underpinning this approach is Item Response Theory (IRT), which models the relationship between a learner’s ability and item characteristics to drive Computerized Adaptive Testing (CAT) [28]. Innovations in IRT—such as memory-based cycles, nonparametric models, and integration with tutoring—have enabled increasingly personalized assessment systems [28–35].

Long-term planning techniques: While IRT-based approaches are powerful for assessment, personalized treatment planning requires more sophisticated long-term decision-making. Non-myopic Bayesian optimization (BO) addresses this need by planning multiple steps ahead, making it particularly well-suited for adaptive speech-language therapy [38–40]. Unlike myopic methods that focus on immediate gain, non-myopic BO methods consider how present actions shape future outcomes. Techniques like GLASSES, BINOCULARS, and rollout-based policies offer efficient strategies for long-horizon planning under uncertainty [41–45], and recent efforts integrate reinforcement learning to adapt interventions directly from observed data [44–46]. These capabilities allow non-myopic BO to dynamically adapt therapeutic interventions over time, optimize treatment plans under cost or time constraints, and ultimately lead to more effective and individualized care in speech-language therapy.

Edge deployment for AI models: To make these AI-driven strategies truly accessible and responsive, edge deployment is essential for scaling up our solution. Recent advances in edge computing and edge AI enable LLMs and optimization-based methods to run directly on resource-constrained edge devices [47, 48, 50]. This paradigm reduces reliance on centralized infrastructure, thereby improving latency, privacy, and cost-effectiveness, which are crucial for healthcare contexts where data sensitivity is paramount [47, 50, 53]. By deploying AI on edge proxies, our system ensures real-time, localized decision-making and assessment, bringing trustworthy and scalable speech-language therapy directly to affected children.

## 3. Experience and Credentials of the Investigators

The investigative team possesses a robust foundation in AI, biomedical engineering, and clinical rehabilitation, with significant contributions directly applicable to the proposed project on applying AI in personalized therapy and effectiveness assessment for developmental language and speech sound disorders in children aged 3-6.

Quan Thanh Tho, Le Thanh Van, and Nguyen Quang Duc have made notable contributions to AI applications in language processing, medical diagnostics, and adaptive learning, which are highly relevant to the proposed project. Tho’s work on a mobile application for translating Vietnamese to Bahnaric using AI demonstrates his experience in handling linguistic data, especially for underrepresented languages, which can be adapted to analyze and model speech patterns in children [71, 72]. Duc’s publication on fine-tuning Vietnamese large language models highlights advanced NLP techniques for processing and evaluating linguistic data, critical for designing AI systems to assess speech sound disorders [73]. Van’s research on leveraging NLP for multilingual support in academic regulations and sentiment analysis for Vietnamese text demonstrates capabilities in processing complex linguistic datasets, which can inform the development of AI-driven speech therapy tools [74, 75].

Le Trong Nhan’s expertise in AI-driven IoT systems and predictive maintenance supports the development of scalable and efficient AI platforms for personalized therapy. His work on deep learning for predictive maintenance and automated data acquisition using optical character recognition and edge computing demonstrates proficiency in designing robust AI systems for real-time data processing, applicable to monitoring children’s therapy progress [76-78].

Ha Thi Thanh Huong, Ngo Thi Lua, Pham Hoang Anh, and Huynh Kim Phat have conducted significant research in neurological, cognitive, mental health, and medical diagnostics using AI, which is pertinent to evaluating the effectiveness of speech therapy interventions. Huong’s work on EEG-based detection of mental disorders and cognitive decline assessment using AI pipelines demonstrates proficiency in analyzing complex physiological data for diagnostic purposes [79, 80]. This expertise can be extended to monitor children's responses during speech therapy. Lua’s research on automated sleep-stage scoring and brain-computer interfaces using AI highlights capabilities in processing biosignals, which could be adapted to analyze speech activity in children [81, 82]. Hoang Anh’s work on AI chatbots for mental health support and customized vocabulary generation using large language models showcases the application of AI in personalized interventions, which can be adapted to create tailored therapeutic content for children with speech disorders [83-85]. Phat’s research on probabilistic modeling of disorder pathogenesis and deep learning for medical diagnostics, such as intraoperative blood loss quantification, demonstrates expertise in developing AI systems for precise health assessments, which can be applied to evaluate therapy effectiveness in children [86-87].

Trinh Huu Tung, Nguyen Thanh Sang, Nguyen Chau Tuyet Nhu, Vu Nguyen Minh Duc, Nguyen Thi Dieu Linh, and Nguyen Ngoc Tuong Vy provide essential clinical and domain expertise from Children's Hospital 2, crucial for the proposed project. Dr. Tung, as the Hospital Director and a pediatric specialist with over 30 years of experience, offers invaluable institutional leadership and broad oversight. Doctor Sang can contribute valuable expertise from his research on the psychological health of vulnerable populations [88]. Tuyet Nhu’s extensive experience as a guest lecturer and clinical practice supervisor in speech therapy, particularly for children with autism spectrum disorders and other problems related to speech, sound and language. This equips the team with practical insights into the therapeutic needs of children with developmental language disorders. Linh and Vy, as practicing speech therapists, contribute hands-on experience in delivering and assessing therapy for pediatric patients. Minh Duc, with recent experience as a physiotherapist at City Children’s Hospital, contributes practical pediatric therapy experience and emerging expertise in biomedical applications, which can bridge clinical practice and AI-driven solutions.

## 4. Approaches

Figure 1: System architecture of our proposed solution. The AI proxy device, equipped with an embedded NVIDIA AI module, processes real-time speech data captured by a multidirectional microphone. The AI-analysed results are transmitted to the therapist’s PC or laptop, where a computer-based software assists in assessment and treatment planning. Data is stored and synchronized via a cloud server, enabling a mobile software on a patient tablet to deliver personalized therapy exercises and track progress remotely.

The investigation will be conducted in four phases, each designed to systematically develop, validate, and implement an AI-driven system for personalized speech and language therapy for children with developmental language disorders. Our solution mainly includes the AI proxy devices, computer-based software for therapists, and a mobile application for patients. An overview of the system architecture of our solution is presented in Figure 1.

Our target is to enhance the current therapy paradigm with the aid of AI techniques. Specifically, the treatment process begins when the child first visits the clinic, where the therapist utilizes the AI proxy device and computer-based software to conduct initial speech and language assessments. The child will take a language test and/or a speech test, depending on their disorder status, on the therapist's computer. The test results, including speech data collected from the multidirectional microphone, will be used to create a surrogate agent that simulates the child's speech and language disorder. Next, we utilize AI-based planning algorithms to analyze multiple treatment scenarios, aiming to select the treatment plans where the surrogate agent shows the most improvement. These plans will be presented to the therapist to assist them in making more personalized treatment decisions for the child.

Figure 2: The proposed therapy paradigm. In clinical settings, the child takes a language and/or speech test on the therapist’s PC/laptop, with speech data captured by a multidirectional microphone. The system leverages the AI proxy device to generate personalized treatment plans, which are reviewed and finalized by the therapist before synchronization to the cloud server. In at-home settings, the child practices AI-personalized exercises on a patient tablet, supervised by parents. Practice results are automatically uploaded to the cloud, enabling therapists to track progress and refine treatment plans in subsequent clinical visits.

After the clinical sessions, the child continues therapy at home using a mobile application on a tablet or smartphone, which delivers personalized exercises aligned with the recommended treatment plan. The exercises can be delivered under gamified activities, enhancing children's engagement during practice. Over time, progress data collected from home-based practice is synchronized to the cloud server and automatically reported to the clinician for review during the next visit. During follow-up visits, the clinician reviews this data, conducts reassessments using the AI proxy device and computer-based software, and adjusts the therapy plan accordingly. This cycle is repeated until the child's speech and language abilities reach age-appropriate norms. We visualize the overall progress of the new therapy paradigm in Figure 2.

We propose four phases to implement our solution: (i) data collection and preparation, (ii) developing an AI proxy device and an adaptive assessment method, (iii) developing a personalized method and applications, and (iv) real-world implementation and evaluation. Phase 1 lays the foundation by collecting and preprocessing essential speech and language data from both children with developmental speech-language disorders and typically developing children. This data serves as the backbone for Phase 2, where AI models and assessment methods are developed. In this second phase, the AI proxy device will also be built, and multimodal learning models will be trained to simulate children’s language-speech development, enabling adaptive assessment and personalized treatment recommendations. These models are then refined in Phase 3, where personalization techniques are applied to tailor treatment plans to individual children. The insights from Phase 2 are used to develop both computer software and mobile applications for integrating AI techniques in real-world use. Finally, in Phase 4, the system is deployed and evaluated in clinical settings, where its effectiveness is compared against traditional therapy methods. The details of these phases are presented below.

Phase 1: Data Collection and Preparation (3 months)

This phase focuses on gathering data and understanding existing treatment and assessment methods for developmental speech and language disorders in children aged 3 – 6. Particularly, we intend to collect disordered children’s demographic information, language-speech assessment results, speech samples, and details of the treatment process, including but not limited to therapist decisions and taken exercises. Collected data will be preprocessed and stored for use in subsequent phases.

- P1.1: Collect and conduct a comprehensive review of current treatment and assessment methodologies for developmental speech and language disorders. This will involve collaborating with speech-language pathologists, collecting and digitizing clinical guidelines, and reviewing literature.

- P1.2: Collect data from at least 150 children aged 3-6 diagnosed with speech sound and developmental language disorders at the children's hospital of Ho Chi Minh City.

- P1.3: Collect data from at least 150 normal developing children aged 3-6 from kindergartens after undergoing specific test from doctors, then collecting demographic information, language-speech test results, and speech samples. The data from these children will be used to jointly build the children's simulation and as the control group to evaluate the children's improvements.

Phase 2: Developing an AI Proxy Device and an Adaptive Assessment Method (12 months)

This phase involves the development of the AI proxy device and multimodal models for simulating children with language-speech developmental disorders.

- P2.1: Develop the AI proxy device, which will serve as the interface for data collection and AI model deployment. Specifically, we intend to build a processing board integrated with an NVIDIA Jetson Orin module with at least 100 TOPS. This board will connect to the multidirectional microphone and the therapist’s computer through USB connections. The role of this AI proxy is to execute speech-collecting commands, simulate children, and analyze the language-speech assessment responses to provide personalized treatment suggestions for therapists.

- P2.2: Analyze the assessment questions and children's responses from collected tests and exercises in P1.1, using Item Response Theory (IRT) [28]. This phase aims to find question/exercise difficulty and relevance information, including question discrimination, guessing factors, and facilitating efficient assessments in later phases.

- P2.3: Develop an adaptive method to evaluate disorder level based on children’s responses (including language and speech) during practice and assessment phases. This will involve analyzing behavioral and performance data based on measurement theory using techniques such as IRT, maximizing Fisher information in psychometrics [28]. In particular, this adaptive method will be integrated into both the therapist’s computer software and the patient’s mobile application. On the therapist's side, this method helps to evaluate disorder level with as few tests as possible, saving time for clinic periods. On the patient side, using the assessment results, our system will automatically generate suitable exercises for children based on expert knowledge.

- P2.4: Develop a multimodal large language model (MLLM) that integrates both speech and text data to simulate a child during the treatment process. The model takes input of  a history of previous questions or exercises, the child's corresponding responses, and a new question. By analyzing the prior questions and responses, the model generates an appropriate response to the new question. To accomplish this, the model must be capable of both receiving and generating text and speech simultaneously, which poses a technical challenge in the current research landscape. This model will be trained on datasets from P1.2 and P1.3 and validated against clinician assessments.

Phase 3: Developing a Personalized Method and Applications (12 months)

This phase focuses on developing the method and applications for personalizing treatment and adaptive assessment for children with developmental speech-language disorders.

- P3.1: Develop methods for personalizing treatment plans:

  - P3.1.1: Develop an adaptation strategy to adapt the general simulation model (P2.4) for an individual child. In detail, we intend to use a child’s responses and speech samples (P1.2 and P1.3) to fine-tune a small part of the MLLM using transfer learning techniques such as Low-rank Adaptation. Data augmentation techniques will be implemented to enhance the diversity of children's data across diverse demographics and disorder levels. The fine-tuning process will be performed locally on the AI proxy device (P2.1) in under 5 minutes. We also implement periodic evaluation while fine-tuning to ensure the model well reflects the child’s current disorder level.

  - P3.1.2: Develop an optimization method utilizing IRT-based question analysis techniques and results (P2.2) to construct treatment plans for maximizing children's improvement in speech-language skills.

  - P3.1.3: Integrate the developed adaptive assessment method (P2.3) into the pipeline to evaluate the children periodically at each clinic visit.

  - P3.1.4: Develop a recommendation method for at-home practice exercises based on domain knowledge and ealect data from at least ch child’s progress. This method will also incorporate the adaptive assessment method (P2.3) to simultaneously evaluate children’s improvement while practicing.

  - P3.1.5: Evaluate the entire personalization pipeline and compare the results with those from traditional therapies using the collected data (P1.2). This phase also involves speech-language therapists in assessing the recommended treatment plans generated by our method to determine their appropriateness and to identify potential personalized treatment decisions that might have been overlooked.

- P3.2: Refine the optimization method (P2.2, P3.1.2) based on feedback from speech-language pathologists. We expect to receive feedback and adjust the appropriateness of the optimization objective, the length of optimization periods, and any relevant factors that should be considered.

- P3.3: Refine the assessment method (P2.3, P3.1.3) based on feedback from speech-language pathologists. We expect to receive feedback and adjust the minimum number of questions in the assessment, the factors that contribute to the disorder level, and the comprehensiveness of the evaluation metrics used.

- P3.4: Develop a computer-based application for therapists to conduct language and speech assessments and integrate P3.1.1–P3.1.3 to recommend personalized treatment plans. The optimization techniques (P3.1.2) will try to recommend plans that can improve the child's simulated responses the most. The software allows therapists to revise assessment results, modify the most suitable treatment plan, before making the final decision for each child.

- P3.5: Develop a mobile application integrating P3.1.2 and P3.1.4 for use by children and their parents. This application will retrieve the therapist's decisions from the cloud server and provide an at-home practice plan with personalized exercises for children.

Phase 4: Real-World Implementation and Evaluation (9 months)

This phase involves deploying the system in clinical settings and evaluating its effectiveness.

- P4.1: Conduct a comparative study between two groups of children with developmental speech-language disorder, one using traditional therapy methods and the other using a personalized AI-driven system. Metrics such as treatment duration, improvement rates, and clinician workload will be compared. Statistical methods (e.g., t-tests, ANOVA) will be used to compare outcomes between the two groups.

- P4.2: Refine assessment and personalization methods based on real-world feedback and data. Qualitative feedback from clinicians and parents will be analyzed thematically to identify strengths and areas for improvement.

New Methodology and Advantages: The project introduces several innovative methodologies:

- AI proxy device for efficient model deployment (P2.1): This device enables local deployment of AI techniques, fostering large-scale deployment of our solution.

- Multimodal language model (P2.4, P3.1.1): The model combines speech and text data as input and output to simulate children during treatment processes, enabling more accurate and personalized therapy planning.

- Adaptive assessment utilizing IRT (P2.2, P2.3): This technique makes the assessment process more efficient, reducing time consumption and overhead workload on therapists.

- Personalized treatment plan with nonmyopic decision-making techniques (P2.2, P3.1.2): Optimizes long-term treatment outcomes, ensuring efficient and effective interventions.

- Personalized at-home exercises (P2.3, P3.1.4): With this approach, the frequency of clinic visits can be reduced while ensuring continuous improvement in children. This helps save time and money for each visit and reduces the workload on therapists.

The project faces several potential technical difficulties and limitations that need to be addressed. First, ensuring sufficient high-quality data for training LLMs, particularly for rare or complex cases, poses a significant challenge. Second, achieving model generalization for diverse populations of children from 3 to 6 years old in the south of Vietnam and variation between boys and girls in speech sound and developmental language disorders is critical, as models must perform effectively beyond the collected datasets they were trained on. Third, ethical and privacy concerns are paramount, requiring robust safeguards to protect sensitive patient information, including personal and speech data, in compliance with privacy regulations. Finally, user adoption presents a hurdle, as therapists and parents must feel comfortable and confident in using the new technology. Addressing these challenges will be essential for the successful implementation and scalability of this solution.

If technical challenges arise, one alternative option is to adopt hybrid models, which combine AI-driven assessments with periodic therapist oversight to strike a balance between automation and human expertise. Another option is implementing simpler rule-based systems for initial speech-language assessments, though this may come at the cost of reduced personalization. Additionally,  teletherapy integration could be used, incorporating remote therapy sessions led by experienced clinicians to complement AI-driven tools and provide a more comprehensive treatment experience. In cases where the selected hardware lacks sufficient VRAM or computational speed, techniques such as model simplification–removing unimportant parameters or employing model compression methods–can be applied to ensure efficient deployment without significantly compromising performance.

## 5. Innovative Technology

This project leverages advanced technologies to support treatment for developmental speech and language disorders in children. Below, we outline the key innovations, their application in the project, and their technical novelties.

1. AI Proxy as the Central Processor: An AI proxy device will serve as the central processor for running multimodal simulations, analyzing assessment and therapy outcomes, and recommending personalized treatment plans. Designed to ease clinicians' workload, it automates routine tasks and delivers actionable, data-driven insights. With real-time data processing, the AI proxy can be integrated into clinical workflows, enabling timely and informed decision-making without deep technical expertise.

2. Multimodal Large Language Models for Patient Simulation: This project develops a multimodal large language model (MLLM) that integrates speech and text to simulate children with language and speech sound disorders. The MLLM analyzes speech patterns, vocabulary, grammar, and fluency to answer test questions, helping therapists predict outcomes and refine therapy plans. This is the first time MLLM has been used to simulate individuals with speech sound and developmental language disorders. Moreover, we intend to use transfer learning for efficient adaptation to each child, reducing computation-intensive scratch training, while real-time updates ensure therapy recommendations remain personalized and responsive to ongoing assessments and at-home exercises.

3. Item Response Theory (IRT) and Adaptive Assessment: We will use IRT to analyze assessment questions and exercises based on difficulty, discrimination, and guessing factors, enabling more accurate insights into a child's abilities. Building on this, an adaptive assessment method will select the most informative questions to maximize accuracy while minimizing effort, resulting in a more efficient and personalized evaluation process for children.

4. Nonmyopic Decision-Making for Long-Term Therapy Optimization: Nonmyopic decision-making algorithms will be used to optimize long-term treatment outcomes. These algorithms prioritize long-term treatment outcomes rather than short-term gains, ensuring that therapy decisions contribute to sustained progress gradually. Moreover, they are integrated with AI models, combining insights from the multimodal LLM and IRT-based assessments to create a comprehensive, forward-looking therapy plan tailored to each child's needs.

5. Gamified Mobile Application for Personalized At-home Practice: This project develops a mobile app that delivers personalized, gamified therapy exercises for children to practice at home. It tracks language and speech responses, provides real-time feedback, and adapts exercises based on each child’s progress. Additionally, cloud integration ensures that all data is securely stored, allowing therapists to monitor progress remotely and refine therapy plans as needed.

## 6. Innovation Roadmap

The proposed research project lays the foundation for several products and solutions that can be developed, implemented, and commercialized over time. Below is a roadmap outlining innovation, product development, commercialization, and the scalability of similar research.

Phase 1: Research and Prototyping (0–24 months)

The project will focus on foundational research and technology development. This includes studying speech and language disorders, as well as current therapy and assessment methods. The team will build and train multimodal large language models using datasets from both children with and without language disorders. Additionally, prototypes for AI proxy devices and a mobile application will be developed. These prototypes will be validated in controlled settings with a small group of children and clinicians to ensure their effectiveness and usability.

Phase 2: Pilot Testing and Refinement (24–36 months)

During this phase, the AI proxy and mobile application will be deployed in partner hospitals and therapy centers to evaluate their effectiveness in real-world clinical and home settings. A comparative study will be conducted to assess the differences between traditional therapy methods and the AI-driven system in terms of treatment outcomes, engagement, and efficiency. Feedback from clinicians, parents, and children will be collected to refine both the system’s usability and therapeutic effectiveness. Additionally, the MLLM and personalized therapy models will be optimized based on real-world data to enhance their accuracy and adaptability.

Phase 3: Product Development and Commercialization (36–48 months)

In this phase, the focus will be on scaling up production and preparing for commercialization. The manufacturing process for AI proxy devices will be developed to support mass production and meet the demand from hospitals and therapy centers. A mobile application for at-home therapy will be publicly launched, targeting parents and children. To facilitate adoption, partnerships will be established with healthcare providers, schools, and insurance companies to integrate the products into existing therapeutic workflows. Additionally, regulatory approvals, such as FDA clearance and CE marking, will be pursued to ensure compliance with medical standards, paving the way for commercial availability in both clinical and consumer markets.

Phase 4: Scaling and Expansion (48+ months)

In this phase, the focus will be on expanding the product line and entering new markets. Additional features will be developed for the mobile application, including multi-dialect support and advanced gamification, to enhance user engagement and accessibility. The technology’s applications will be explored in related fields, such as autism spectrum disorder (ASD) and hearing impairment, broadening its impact. Expansion into international markets will begin, prioritizing regions with similar challenges in speech and language therapy. To further extend accessibility, partnerships will be established with global health organizations and NGOs, ensuring that the technology reaches underserved populations.

Applicability of the Proposed Research Problem: The proposed research tackles a critical and growing challenge in pediatric healthcare by leveraging AI to enhance the accessibility, personalization, and efficiency of speech and language therapy. Scalability is a key advantage, as the AI-driven system can be deployed in both urban and rural settings, addressing the widespread shortage of well-trained speech-language pathologists. By automating assessments and treatment planning, the system ensures that children, regardless of their location, receive high-quality care. Personalization is another crucial aspect, as the technology tailors therapy plans based on each child’s unique needs, learning patterns, and progress, leading to more effective and engaging treatment. Accessibility is significantly improved through the mobile application, which enables at-home therapy, reducing the burden of frequent clinic visits on families while maintaining consistent treatment progress. Finally, cost-effectiveness is achieved by optimizing therapy plans, lowering the financial burden on both families and healthcare providers while increasing the efficiency of therapeutic interventions.

Ability to Commercialize the Products: The proposed technology has strong commercial potential due to its innovative features, scalability, and alignment with market demands. Healthcare providers, including hospitals, therapy centers, and clinics, can integrate this solution to enhance their speech and language therapy services, improving both efficiency and overall patient outcomes. Schools and educational institutions can adopt the technology to support children with language disorders within special education programs. Parents and families benefit from an affordable and convenient at-home therapy solution through the mobile application, ensuring continuous support outside of clinical settings. Insurance companies may incorporate the technology into coverage plans, as it improves therapy outcomes while reducing long-term treatment costs. The commercialization strategy includes multiple revenue streams, such as hardware and software licensing for AI proxy devices used by healthcare providers and schools. A tiered subscription model could be offered for the mobile app, while data analytics services will provide insights from aggregated, anonymized data. Strategic partnerships with NGOs and government agencies can facilitate the deployment of this solution in underserved regions through grants and public-private collaborations, expanding its accessibility for more children.

## 7. Tentative Schedule and Metrics

Phase 1: Data Collection and Preparation (M1–M3)

| Activity | Timeline | Metrics |
| --- | --- | --- |
| P1.1: Collect treatment and assessment methodologies | Month 1 | Literature review completed; clinical guidelines digitized |
| P1.2: Collect data from 150 children with speech sound and developmental language disorders in children | Months 1–3 | 150 data points collected and annotated |
| P1.3: Collect data from 150 typically normal developing children | Months 1–3 | 150 data points collected and annotated |
| Data preprocessing and storage Initial exploratory analysis and descriptive statistics | Month 3 | Data structured and validated for analysis; Summary statistics and correlation patterns identified |

Phase 2: Developing an AI Proxy Device and an Adaptive Assessment Method (M4-M15)

| Activity | Timeline | Metrics |
| --- | --- | --- |
| P2.1: Develop AI proxy hardware | Months 4–6 | Functional prototype with Jetson Orin module (100+ TOPS) |
| P2.2: Analyze assessment questions using IRT | Months 4–9 | Difficulty, discrimination, and guessing parameters computed for collected questions and exercises |
| P2.3: Develop an adaptive disorder evaluation method | Months 7–12 | The method was built and validated with P1.2/P1.3 data |
| P2.4: Build a multimodal LLM for child simulation | Months 10–15 | Model trained and benchmarked against clinician assessments |

Phase 3: Developing a Personalized Method and Applications (M16–M27)

| Activity | Timeline | Metrics |
| --- | --- | --- |
| P3.1.1: Adapt the general simulation model to individual children | Months 16–19 | Personalization strategy validated with test children |
| P3.1.2: Build a non-myopic optimization method to construct personalized treatment plans | Months 17–20 | Method for constructing treatment plans evaluated for effective improvement |
| P3.1.3: Integrate adaptive assessment method into workflow | Months 19–20 | Adaptive assessment method integrated running without error |
| P3.1.4: Develop a recommendation system for at-home exercises | Months 19–22 | Recommendation evaluated by therapists with accuracy above 85% compared to experienced therapists |
| P3.1.5: Evaluate the entire personalization pipeline | Months 22–24 | Comparative study with traditional therapies in simulation |
| P3.2: Refine optimization method | Months 22–27 | The optimization method can provide treatment plans with more than 80% similarity to experienced therapists. |
| P3.3: Refine assessment method | Months 22–27 | The assessment method can operate with >= 90% accuracy with the minimum number of questions. |
| P3.4: Develop a computer-based therapist application | Months 22–24 | Functional prototype tested in clinical settings |
| P3.5: Develop a mobile application for children/parents | Months 24–27 | Initial app deployed for beta testing |

Phase 4: Real-World Implementation and Evaluation (M28–M36)

| Activity | Timeline | Metrics |
| --- | --- | --- |
| P4.1: Conduct a comparative study between AI-driven and traditional therapy | Months 28–33 | Statistical significance in children's improvement rates with at least 50 children |
| P4.2: Refine assessment and personalization based on feedback | Months 34–36 | Iterative updates improving usability and performance |

# D. PROJECT ACTIVITIES

(What are the specific activities that will happen during the project? Include a Gantt chart if possible, as it shows that you’ve planned effectively and helps financiers understand project timelines.)

The project “Application of Artificial Intelligence in Personalized Therapy and Effectiveness Assessment of Developmental Language and Speech Sound Disorders in Children Aged 3–6” will be implemented across four main phases:

- Phase 1: Collect and preprocess data from participating children.

- Phase 2: Develop an AI proxy device, an adaptive assessment system, and a general multimodal large language model to simulate children’s language and speech sound disorders.

- Phase 3: Design and evaluate a personalized long-term treatment planning method, create a recommendation system for at-home exercises, and build both the clinician-facing software and the child-facing mobile application.

- Phase 4: Deploy the developed solutions with a group of experimental participants, collect results, and refine the system based on feedback.

A detailed timeline with corresponding team members is presented below.

| No. | Activity | Timeline | Persons in Charge |
| --- | --- | --- | --- |
| P1.1 | Collect treatment and assessment methodologies | Month 1 | Quan Thanh Tho, Le Thanh Van, Ha Thi Thanh Huong, Ngo Thi Lua, Huynh Kim Phat, Trinh Huu Tung, Nguyen Thanh Sang. Nguyen Chau Tuyet Nhu, Vu Nguyen Minh Duc, Nguyen Thi Dieu Linh, Nguyen Ngoc Tuong Vy |
| P1.2 | Collect data from 150 children with speech-language disorders | Months 1–3 |  |
| P1.3 | Collect data from 150 typically developing children | Months 1–3 |  |
| P1.2 + P1.3 | Data preprocessing and storage Initial exploratory analysis and descriptive statistics | Month 3 |  |
| P2.1 | Develop AI proxy hardware | Months 4–6 | Quan Thanh Tho, Pham Hoang Anh, Le Trong Nhan, Le Thanh Van, Ha Thi Thanh Huong, Ngo Thi Lua, Huynh Kim Phat, Nguyen Quang Duc |
| P2.2 | Analyze assessment questions using IRT | Months 4–9 |  |
| P2.3 | Develop an adaptive disorder evaluation method | Months 7–12 |  |
| P2.4 | Build a multimodal LLM for child simulation | Months 10–15 | Quan Thanh Tho, Pham Hoang Anh, Le Trong Nhan, Le Thanh Van, Ha Thi Thanh Huong, Ngo Thi Lua, Huynh Kim Phat, Trinh Huu Tung, Nguyen Thanh Sang, Nguyen Chau Tuyet Nhu, Nguyen Quang Duc, Vu Nguyen Minh Duc, Nguyen Thi Dieu Linh, Nguyen Ngoc Tuong Vy |
| P3.1.1 | Adapt the general simulation model to individual children | Months 16–19 | Quan Thanh Tho, Pham Hoang Anh, Le Trong Nhan, Le Thanh Van, Ha Thi Thanh Huong, Ngo Thi Lua, Huynh Kim Phat, Nguyen Quang Duc |
| P3.1.2 | Build a non-myopic optimization method to construct personalized treatment plans | Months 17–20 |  |
| P3.1.3 | Integrate adaptive assessment method into workflow | Months 19–20 | Quan Thanh Tho, Pham Hoang Anh, Le Trong Nhan, Le Thanh Van, Ha Thi Thanh Huong, Ngo Thi Lua, Huynh Kim Phat, Trinh Huu Tung, Nguyen Thanh Sang, Nguyen Chau Tuyet Nhu, Nguyen Quang Duc, Vu Nguyen Minh Duc, Nguyen Thi Dieu Linh, Nguyen Ngoc Tuong Vy |
| P3.1.4 | Develop a recommendation system for at-home exercises | Months 19–22 |  |
| P3.1.5 | Evaluate the entire personalization pipeline | Months 22–24 |  |
| P3.2 | Refine optimization method | Months 22–27 |  |
| P3.3 | Refine assessment method | Months 22–27 |  |
| P3.4 | Develop a computer-based therapist application | Months 22–24 | Quan Thanh Tho, Pham Hoang Anh, Le Trong Nhan, Le Thanh Van, Ha Thi Thanh Huong, Ngo Thi Lua, Huynh Kim Phat, Trinh Huu Tung, Nguyen Thanh Sang, Nguyen Quang Duc |
| P3.5 | Develop a mobile application for children/parents | Months 24–27 |  |
| P4.1 | Conduct a comparative study between AI-driven and traditional therapy | Months 28–33 | Trinh Huu Tung, Nguyen Thanh Sang. Nguyen Chau Tuyet Nhu, Vu Nguyen Minh Duc, Nguyen Thi Dieu Linh, Nguyen Ngoc Tuong Vy |
| P4.2 | Refine assessment and personalization based on feedback | Months 34–36 | Quan Thanh Tho, Pham Hoang Anh, Le Trong Nhan, Le Thanh Van, Ha Thi Thanh Huong, Ngo Thi Lua, Huynh Kim Phat, Trinh Huu Tung, Nguyen Thanh Sang. Nguyen Chau Tuyet Nhu, Vu Nguyen Minh Duc, Nguyen Thi Dieu Linh, Nguyen Ngoc Tuong Vy |

The execution timeline of each activity is outlined in the Gantt chart below

# E. PROJECT RESULTS

What are the results of your planned project? How will you evaluate them?

| No. | Productions | Quality | Notes |
| --- | --- | --- | --- |
| 1 | Products, services, solutions-oriented applications that will bring real benefits to the community. | 4 | Four sets of products for deploying our solution. Each set mainly contains the NVIDIA Jetson Orin and a multidirectional microphone. |
| 2 | International Publications | 7 | 2 top journal or conference papers (Q1/A/A*) and 5 papers in other journals and conferences |
| 3 | National Publications | 0 |  |
| 4 | Patent | 1 | 1 Vietnam or US Patient about the proposed solution |
| 5 | Education and training | 4 | 1 Doctor of Philosophy and 3 Master |
| 6 | Others | 0 |  |

# F. PROJECT IMPACTS

The proposed project, AI-Driven Personalized Speech and Language Therapy for Children, will have significant academic and real-world impacts across short-term, medium-term, and long-term horizons. Below is a detailed breakdown of the expected outcomes and impacts:

Short-Term Impacts (Completion – 6 months)

Academic Impacts:

- Publication of findings: Results from the pilot testing and comparative study will be published in high-impact journals, contributing to the body of knowledge in speech-language pathology, AI in healthcare, and pediatric therapy.

- Open datasets: The curated datasets (speech samples and behavioral responses) will be made available to the research community with protected privacy, fostering further innovation and collaboration.

- Validation of novel methods: The project will validate the use of multimodal LLMs, adaptive testing, and long-term personalized therapy in speech and language therapy, setting a precedent for future research.

Real-World Impacts:

- Improved access to therapy: The mobile application and AI suite (AI devices and computer-based software) will be deployed in partner hospitals and therapy centers, providing immediate access to personalized therapy for children with speech and language disorders.

- Reduced burden on clinicians: The AI proxy and automated assessment tools will reduce the workload on speech-language pathologists, allowing them to focus on complex cases.

- Enhanced therapy outcomes: Children using the system will experience measurable improvements in language skills, such as speech clarity, vocabulary size, and sentence complexity.

Medium-Term Impacts (6 months – 2 years)

Academic Impacts:

- Expansion of research scope: The project will inspire further research into the application of AI, especially AI for healthcare and education, such as autism spectrum disorder (ASD) and hearing impairment.

- Development of new theories: Insights from the project will contribute to the development of new theories in measurement theory, nonmyopic decision-making, and adaptive learning and testing.

- Interdisciplinary collaboration: The project will foster collaboration between computer scientists, neuroscientists, and speech-language pathologists, leading to innovative interdisciplinary research.

Real-World Impacts:

- Scalability and adoption: The system will be scaled to additional hospitals, schools, and therapy centers, reaching a larger population of children with speech and language disorders.

- Commercialization: All the solutions can be commercialized, generating revenue and ensuring the sustainability of the project.

- Policy influence: The success of the project will influence healthcare policies, encouraging the integration of AI-driven tools into standard therapy practices.

- Global reach: The technology will be adapted for use in other languages and regions, addressing the global shortage of speech-language pathologists.

Long-Term Impacts (2+ years)

Academic Impacts:

- Establishment of new research fields: The project will pave the way for new research fields, such as AI-driven personalized therapy and neurocomputational models of language development.

- Training the next generation: The project will serve as a training ground for Master’s, PhD students, and researchers in AI, neuroscience, and speech-language pathology, creating a pipeline of skilled professionals.

- Longitudinal studies: The availability of long-term data from the project will enable longitudinal studies on the effectiveness of personalized therapy and its impact on children’s development.

Real-World Impacts:

- Transformation of therapy practices: The widespread adoption of AI-driven tools will transform speech and language therapy, making it more personalized, efficient, and accessible.

- Improved quality of life for patients: Children with developmental speech and language disorders will experience long-term improvements in communication skills, academic performance, and social integration.

- Economic benefits: By reducing the cost of therapy and improving outcomes, the project will generate significant economic benefits for families, healthcare systems, and society as a whole.

- Global health impact: The technology will be deployed in low-resource settings, addressing health disparities and improving access to therapy for underserved populations.

# G. REFERENCES CITED

(Length unlimited and not part of the 15-page limit.)

- Simon, P., and Rosenbaum, S., Speech and language disorders in children: Implications for the social security administration's supplemental security income program. National Academies Press, 2016.

- Laasonen, M., et al. "Understanding developmental language disorder-the Helsinki longitudinal SLI study (HelSLI): a study protocol," in BMC psychology, vol. 6, pp. 1–13, 2018.

- Danubianu, M., et al, "Distributed intelligent system for personalized therapy of speech disorders," in 2008 The Third International Multi-Conference on Computing in the Global Information Technology (iccgi 2008), 2008, pp. 166–170.

- Danubianu, M., et al. "TERAPERS-intelligent solution for personalized therapy of speech disorders," in International Journal On Advances in Life Sciences, vol. 1, no. 1, pp. 26–35, 2009.

- Danubianu, M., Pentiuc, S., and Socaciu, T., "Towards the optimized personalized therapy of speech disorders by data mining techniques," in 2009 Fourth International Multi-Conference on Computing in the Global Information Technology, 2009, pp. 20–25.

- Danubianu, M., et al. "Advanced Information Technology-support of improved personalized therapy of speech disorders," in International Journal of Computers Communications & Control, vol. 5, no. 5, pp. 684–692, 2010.

- Parekh, A., et al. "Artificial intelligence (AI) in personalized medicine: AI-generated personalized therapy regimens based on genetic and medical history," in Annals of Medicine and Surgery, vol. 85, no. 11, pp. 5831–5833, 2023.

- Schork., N., "Artificial intelligence and personalized medicine," in Precision medicine in Cancer therapy, pp. 265–283, 2019.

- Bhardwaj, A., et al. "Transforming pediatric speech and language disorder diagnosis and therapy: the evolving role of artificial intelligence," in Health Sciences Review, pp. 100188, 2024.

- Gao, C., et al. "Large language models empowered agent-based modeling and simulation: A survey and perspectives," in Humanities and Social Sciences Communications, vol. 11, no. 1, pp. 1–24, 2024.

- Asfour, M., and Murillo, J., "Harnessing large language models to simulate realistic human responses to social engineering attacks: A case study," in International Journal of Cybersecurity Intelligence & Cybercrime, vol. 6, no. 2, pp. 21–49, 2023.

- Solera-Monforte, S., Arnau-Gonzalez, P., and Arevalillo-Herráez, M., "Be My Mate: Simulating Virtual Students for collaboration using Large Language Models," in Proceedings of the 17th International Natural Language Generation Conference: System Demonstrations, 2024, pp. 1–3.

- Sonkar, S., and Baraniuk, R., "Deduction under Perturbed Evidence: Probing Student Simulation (Knowledge Tracing) Capabilities of Large Language Models.," in LLM@AIED, 2023, pp. 26–33.

- Benedetto, L., et al, "Using LLMs to simulate students’ responses to exam questions," in Findings of the Association for Computational Linguistics: EMNLP 2024, 2024, pp. 11351–11368.

- Lu, X., and Wang, X., "Generative students: Using llm-simulated student profiles to support question item evaluation," in Proceedings of the Eleventh ACM Conference on Learning@ Scale, 2024, pp. 16–27.

- Sharma, P., and Li, Q., "Designing Simulated Students to Emulate Learner Activity Data in an Open-Ended Learning Environment," in Proceedings of the 17th International Conference on Educational Data Mining, 2024, pp. 986–989.

- Brugge, E., et al. "Large language models improve clinical decision making of medical students through patient simulation and structured feedback: a randomized controlled trial," in BMC Medical Education, vol. 24, no. 1, pp. 1391, 2024.

- Holderried, F., et al. "A language model–powered simulated patient with automated feedback for history taking: Prospective study," in JMIR Medical Education, vol. 10, no. 1, pp. e59213, 2024.

- Yamamoto, A., et al. "Enhancing Medical Interview Skills Through AI-Simulated Patient Interactions: Nonrandomized Controlled Trial," in JMIR Medical Education, vol. 10, no. 1, pp. e58753, 2024.

- Reichenpfader, D., and Denecke, K., "Simulating diverse patient populations using patient vignettes and large language models," in Proceedings of the First Workshop on Patient-Oriented Language Processing (CL4Health)@ LREC-COLING 2024, 2024, pp. 20–25.

- Cook, D., "Creating virtual patients using large language models: scalable, global, and low cost," in Medical teacher, vol. 47, no. 1, pp. 40–42, 2025.

- Benfatah, M., et al. "Assessing the efficacy of ChatGPT as a virtual patient in nursing simulation training: A study on nursing students' experience," in Teaching and Learning in Nursing, vol. 19, no. 3, pp. e486–e493, 2024.

- Chaby, L., et al. "Embodied virtual patients as a simulation-based framework for training clinician-patient communication skills: An overview of their use in psychiatric and geriatric care," in Frontiers in virtual reality, vol. 3, pp. 827312, 2022.

- Wang, R., et al, "PATIENT-𝜓: Using Large Language Models to Simulate Patients for Training Mental Health Professionals," in Proceedings of the 2024 Conference on Empirical Methods in Natural Language Processing, 2024, pp. 12772–12797.

- Lee, J., et al. "Analyzing evaluation methods for large language models in the medical field: a scoping review," in BMC Medical Informatics and Decision Making, vol. 24, no. 1, pp. 366, 2024.

- Tilala, M., et al. "Ethical considerations in the use of artificial intelligence and machine learning in health care: a comprehensive review," in Cureus, vol. 16, no. 6, 2024.

- Ferrario, A., Sedlakova, J., and Trachsel, M., "The role of humanization and robustness of large language models in conversational artificial intelligence for individuals with depression: a critical analysis," in JMIR Mental Health, vol. 11, pp. e56569, 2024.

- Bock, R., and Gibbons, R., Item response theory. John Wiley & Sons, 2021.

- Xu, X., and Douglas, J., “Computerized adaptive testing under nonparametric IRT models,” Psychometrika, vol. 71, no. 1, pp. 121–137, 2006.

- Liu, C., et al, "Research on computerized adaptive testing system based on IRT," in 2010 Seventh International Conference on Fuzzy Systems and Knowledge Discovery, 2010, pp. 1817–1821.

- Riza, L., Nurjanah, N., and Wihardi, Y., "The development of computer adaptive test and item response theory with 4 parameters based the logistics model," in Journal of Physics: Conference Series, 2019, pp. 032033.

- Runzrat, S., Harfield, A., and Charoensiriwath, S., "Applying item response theory in adaptive tutoring systems for Thai language learners," in 2019 11th International Conference on Knowledge and Smart Technology (KST), 2019, pp. 67–71.

- Vesin, B., et al. "Adaptive assessment and content recommendation in online programming courses: On the use of Elo-rating," in ACM Transactions on Computing Education (TOCE), vol. 22, no. 3, pp. 1–27, 2022.

- Şimşek, A. S., and Tavşancıl, E., “Applicability and efficiency of a polytomous IRT-Based computerized adaptive test for measuring psychological traits,” Journal of Measurement and Evaluation in Education and Psychology, vol. 13, no. 4, pp. 328–344, 2022.

- Yang, A., Flanagan, B., and Ogata, H., "Adaptive formative assessment system based on computerized adaptive testing and the learning memory cycle for personalized learning," in Computers and Education: Artificial Intelligence, vol. 3, pp. 100104, 2022.

- Xu, L., et al. "Developing Computerized Adaptive Testing for a National Health Professionals Exam: An Attempt from Psychometric Simulations," in Perspectives on Medical Education, vol. 12, no. 1, 2023.

- Sharpnack, J., et al., “BanditCAT and AutoIRT: Machine Learning Approaches to Computerized Adaptive Testing and Item Calibration,” in Proceedings of Large Foundation Models for Educational Assessment, Dec. 2025, vol. 264, pp. 121–135.

- Gonzalez, J., Osborne, M., and Lawrence, N., “GLASSES: Relieving the myopia of Bayesian optimisation,” In Artificial Intelligence and Statistics, pp. 790–799, 2016.

- Snoek, J., Larochelle, H., and Adams, R. P., “Practical Bayesian optimization of machine learning algorithms,” in Advances in Neural Information Processing Systems, vol. 4, pp. 2951–2959, 2012.

- Wu, J. and Frazier, P., “Practical two-step lookahead Bayesian optimization,” in Advances in neural information processing systems, vol. 32, 2019.

- Yue, X. and Kontar, R. A., “Why non-myopic Bayesian optimization is promising, and how far should we look ahead? a study via rollout,” in International Conference on Artificial Intelligence and Statistics, pp. 2808–2818, 2020.

- Jiang, S., Chai, H., Gonzalez, J., and Garnett, R., “BINOCULARS for efficient, nonmyopic sequential experimental design,” in International Conference on Machine Learning, pp. 4794–4803, 2020.

- Jiang, S., Jiang, D., Balandat, M., Karrer, B., Gardner, J., and Garnett, R., “Efficient nonmyopic Bayesian optimization via one-shot multi-step trees,” in Advances in Neural Information Processing Systems, vol. 33, pp. 18039–18049, 2020.

- Astudillo, R., Jiang, D., Balandat, M., Bakshy, E., and Frazier, P., “Multi-step budgeted Bayesian optimization with unknown evaluation costs,” in Advances in Neural Information Processing Systems, vol.34, pp. 20197–20209, 2021.

- Lee, E. H., Eriksson, D., Perrone, V., and Seeger, M., “A nonmyopic approach to cost-constrained Bayesian optimization,” in Proceedings of the Thirty-Seventh Conference on Uncertainty in Artificial Intelligence, pp. 568–577. PMLR, 2021.

- Cheon, M., Byun, H., and Lee, J. H., “Non-myopic Bayesian optimization using model-free reinforcement learning and its application to optimization in electrochemistry,” Computers & Chemical Engineering, vol. 184, p. 108624, 2024.

- Su, W., Li, L., Liu, F., He, M., and Liang, X., “AI on the edge: a comprehensive review,” Artificial Intelligence Review, vol. 55, no. 8, pp. 6125–6183, 2022.

- Situnayake, D., and Plunkett, J., AI at the Edge. “ O’Reilly Media, Inc.,” 2023.

- Deng, S., Zhao, H., Fang, W., Yin, J., Dustdar, S., and Zomaya, A. Y., “Edge intelligence: The confluence of edge computing and artificial intelligence,” IEEE Internet of Things Journal, vol. 7, no. 8, pp. 7457–7469, 2020.

- Singh, R., and Gill, S. S., “Edge AI: a survey,” Internet of Things and Cyber-Physical Systems, vol. 3, pp. 71–92, 2023.

- Tuli, S., et al., “AI augmented Edge and Fog computing: Trends and challenges,” Journal of Network and Computer Applications, vol. 216, p. 103648, 2023.

- Nandhakumar, A. R., Baranwal, A., Choudhary, P., Golec, M., and Gill, S. S., “EdgeAISim: A toolkit for simulation and modelling of AI models in edge computing environments,” Measurement: Sensors, vol. 31, p. 100939, 2024.

- Zagar, P., Ravi, V., Aalami, L., Krusche,  S., Aalami, O., and Schmiedmayer, P., “Dynamic fog computing for enhanced LLM execution in medical applications,” Smart Health, p. 100577, 2025.

- R. E. Owens, Jr., "First words and word combinations in toddler talk," in Language development: An introduction, 9th ed. Pearson, 2016, ch. 7, pp. 185–196.

- A. Sansavini et al., “Developmental language disorder: Early predictors, age for the diagnosis, and diagnostic tools. A scoping review,” Brain sciences, vol. 11, no. 5, p. 654, 2021.

- D. V. Bishop et al., “Phase 2 of CATALISE: A multinational and multidisciplinary Delphi consensus study of problems with language development: Terminology,” Journal of child psychology and psychiatry, vol. 58, no. 10, pp. 1068–1080, 2017.

- C. F. Norbury et al., “The impact of nonverbal ability on prevalence and clinical presentation of language disorder: Evidence from a population study,” Journal of child psychology and psychiatry, vol. 57, no. 11, pp. 1247–1257, 2016.

- A. Roman-Urrestarazu, R. van Kessel, C. Allison, F. E. Matthews, C. Brayne, and S. Baron-Cohen, “Association of race/ethnicity and social disadvantage with autism prevalence in 7 million school children in England,” JAMA pediatrics, vol. 175, no. 6, pp. e210054–e210054, 2021.

- K. Sayal, V. Prasad, D. Daley, T. Ford, and D. Coghill, “ADHD in children and young people: prevalence, care pathways, and service provision,” The lancet psychiatry, vol. 5, no. 2, pp. 175–186, 2018.

- P. Eadie, A. Morgan, O. C. Ukoumunne, K. Ttofari Eecen, M. Wake, and S. Reilly, “Speech sound disorder at 4 years: Prevalence, comorbidities, and predictors in a community cohort of children,” Developmental Medicine & Child Neurology, vol. 57, no. 6, pp. 578–584, 2015.

- S. Harding, S. Burr, J. Cleland, H. Stringer, and Y. Wren, “Outcome measures for children with speech sound disorder: an umbrella review,” BMJ open, vol. 14, no. 4, p. e081446, 2024.

- L. D. Shriberg, J. B. Tomblin, and J. L. McSweeny, “Prevalence of speech delay in 6-year-old children and comorbidity with language impairment,” Journal of speech, language, and hearing research, vol. 42, no. 6, pp. 1461–1481, 1999.

- S. Harding, S. Burr, J. Cleland, H. Stringer, and Y. Wren, “Outcome measures for children with speech sound disorder: an umbrella review,” BMJ open, vol. 14, no. 4, p. e081446, 2024.

- J. N. Kaderavek, "Assessment of language disorder," in Language disorders in children: Fundamental concepts of assessment and intervention, 2nd ed., Pearson, 2015, pp. 46–51.

- R. Paul and C. Norbury, "Assessment," in Language Disorders from Infancy Through Adolescence, Elsevier Health Sciences, 2012, pp. 38–55.

- J. E. Bernthal, N. W. Bankson, and P. Flipsen Jr., "Assessment: Data Collection," in Speech Sound Disorders in Children, 9th ed. Pearson Publishing, 2017, pp. 150–175.

- American Speech-Language-Hearing Association, "Speech sound disorders: Articulation and phonology," n.d. [Online]. Available: https://www.asha.org/practice-portal/clinical-topics/articulation-and-phonology/. [Accessed: Apr. 8, 2025].

- S. Rinaldi et al., “Efficacy of the treatment of developmental language disorder: A systematic review,” Brain sciences, vol. 11, no. 3, p. 407, 2021.

- A. M. Chilosi et al., “Reading and spelling disabilities in children with and without a history of early language delay: A neuropsychological and linguistic study,” Child Neuropsychology, vol. 15, no. 6, pp. 582–604, 2009.

- D. Calder, M. Claessen, S. Leitão, and S. Ebbels, “Evaluating two different dose frequencies and cumulative intervention intensities to improve past tense production for early school-aged children with developmental language disorder,” International Journal of Language & Communication Disorders, vol. 56, no. 6, pp. 1278–1295, 2021.

- T. Q. Thanh et al., “BaNaVA: A Cross-Platform AI Mobile Application for Preserving the Bahnaric Languages,” Proc. 8th IEEE/ACIS Int. Conf. Big Data, Cloud Comput., Data Sci. (BCD), Ho Chi Minh City, Vietnam, 2023.

- K. N. H. Vo et al., “Revitalizing Bahnar Language Through Neural Machine Translation: Challenges, Strategies, and Promising Outcomes,” Proc. 14th Symp. Educ. Adv. Artif. Intell. (EAAI-24), Vancouver, Canada, 2024.

- S. T. Truong et al., “Crossing Linguistic Horizons: Finetuning and Comprehensive Evaluation of Vietnamese Large Language Models,” Proc. 2024 Annu. Conf. North Amer. Chapter Assoc. Comput. Linguist. (NAACL-24), Mexico City, Mexico, 2024.

- Son-Tin Nguyen, Dinh-Tuan Nguyen, and Thanh-Van Le, "Leveraging NLP for Multilingual Support in Academic Regulations," Communications in Computer and Information Science, vol. 2191, pp. 304–312, 2024.

- Tri Cong-Toan Tran, Thien Phu Nguyen, and Thanh-Van Le, "HSUM-HC: Integrating BERT-Based Hidden Aggregation to Hierarchical Classifier for Vietnamese Aspect-Based Sentiment Analysis," Proceedings of the 8th NAFOSTED Conference on Information and Computer Science (NICS), Hanoi, Vietnam, 2022.

- Minh Tai Pham Nguyen, Minh Khue Phan Tran, and Trong Nhan Le, “An Efficient Configuration Based on Deep Learning Models for Predictive Maintenance of Solar-Powered IoT Devices,” Lecture Notes on Data Engineering and Communications Technologies, vol. 2, pp. 113–122, 2024.

- Phuc Ho Trong, Phuc Vinh Tran, Phat Nguyen Hong, Trong Nhan Le, “Automated Data Acquisition for Water Metering System Using Narrowband Internet of Things and Optical Character Recognition Engine,” Proc. Int. Conf. Adv. Technol. Commun. (ATC), 2024, pp. 1–12.

- Thien An Nguyen, Nhu Hung Huynh, Trong Nhan Le, “Edge computing for wireless sensor network,” Proc. Int. Conf. Intelligence of Things (ICIot), vol. 148, pp. 87–97, 2022.

- L. Ngo, A. Le, K. Ho, T. Le, N. Nguyen, S. Nguyen, D. Duong, and H. Ha, “Electroencephalogram (EEG) based automated detection of mental disorders using artificial intelligence processing pipelines,” Neuroscience Research Notes (Accepted), 2025.

- Thanh Truc-Quynh Nguyen, Chau Bao Dinh Hoang, Minh Dung Hoang Le, Ngoc Tram Anh V, Halle Quang, Christopher Minh Nguyen, Claire Goodman, George M Savva, Van Luan Pham, Trung Thu Tran, Van Toi Vo, and Thi Thanh Huong Ha, "Assessing cognitive decline in Vietnamese older adults using the Montreal Cognitive Assessment-Basic (MoCA-B) and Informant Questionnaire on Cognitive Decline in the Elderly (IQCODE) during the COVID-19 pandemic: a feasibility study," in The Clinical Neuropsychologist, vol. 37, no. 5, pp. 1043–1061, 2023.

- T. Luu, A. Dang-Hieu, T. Ly, H. P. Thanh, H. Ha, and L. Ngo, “Developing a photoplethysmography-based automated sleep-stage scoring framework using artificial intelligence,” in Proc. 10th Int. Conf. Vietnam Dev. Biomed. Eng., 2023.

- T.-H. Nguyen, P.-D. Sam, L. Ngo, and H.-D. Nguyen, “Thinking-Computer Control System (TCCS) for remotely controlling electronic devices by brainwaves – An assistive BCI system for people with motor-impaired disabilities,” in Proc. 10th Int. Conf. Vietnam Dev. Biomed. Eng., 2023.

- Vo Ngoc Sang, Nguyen Ngoc Thanh Xuan, Pham Tan Phuoc, Pham Hoang Anh, “Beyond Textbooks: A Novel Workflow for Customized Vocabulary Sheet Generation with Large Language Models,” Lecture Notes on Data Engineering and Communications Technologies, vol. 230, pp. 208–220, 2024.

- Vo Ngoc Sang, Nguyen Ngoc Thanh Xuan, Pham Tan Phuoc, Nguyen Quoc Viet, Pham Hoang Anh, “Enhancing AI Chatbots for Mental Health Support: A Comprehensive Approach,” Lecture Notes in Computer Science, vol. 15431, p. 12, 2024.

- Xuan Ngoc-Thanh Nguyen, Sang Ngoc Vo, Hoang-Anh Pham, “Mental Chatbot Application Using Retrieval Augmented Generation,” Lecture Notes in Networks and Systems, vol. 23, pp. 363–375, 2024.

- Huynh, P. K., Setty, A., Phan, H., and Le, T. Q., "Probabilistic domain-knowledge modeling of disorder pathogenesis for dynamics forecasting of acute onset," in Artificial Intelligence in Medicine, vol. 115, pp. 102056, 2021.

- Nguyen, Dang, Minh Huu Nhat, Le, Trung Q., Le, Chinyere, Charles-Okezie, Michael J., Diaz, Cameron, Sabet, Hung The, Dang, Tuan, Nguyen, Hoan, Nguyen, Minh, Tran, Nguyen Quoc Khanh, Le, Aaron, Muncey, and Phat K., Huynh, "Deep Learning-based Integrated System for Intraoperative Blood Loss Quantification in Surgical Sponges," in IEEE Journal of Biomedical and Health Informatics, pp. 1-11, 2024.

- Thanh Sang, Nguyen, “The Impact of COVID-19 on the Psychological Health of Pregnant Women,” Vietnam Journal of Psychology, no. 7, 2022.

# H. BIOGRAPHICAL SKETCH

BIOGRAPHICAL SKETCH

## Name: Quan Thanh Tho

Position title: Dean of the Faculty of Computer Science and Engineering, Ho Chi Minh City University of Technology - VNU-HCM, Vietnam

Education/training

| Institution and location | Degree | Completion date | Field of study |
| --- | --- | --- | --- |
| Ho Chi Minh City University of Technology - VNU-HCM, Vietnam | Bachelor of Engineering | 04/1998 | Information Technology |
| Nanyang Technological University, Singapore | Doctor of Philosophy | 06/2006 | Computer Science |

I. Personal Statement

As Dean of the Faculty of Computer Science and Engineering at HCMUT, I have led efforts to advance AI research and foster academic–industry collaboration in Vietnam and internationally. With a Ph.D. from NTU Singapore and over 20 years of experience, my expertise spans formal methods, program analysis, machine learning, and semantic web technologies.

Through my leadership of the Unlimited Research Group on AI (URA), I’ve collaborated with institutions such as Stanford, EPFL, NTU, and companies like Bosch and FPT. I have led impactful projects in healthcare and education, including fake medical news detection and Vietnamese-Bahnaric machine translation, and spearheaded the development of URA-LLaMa, a fine-tuned Vietnamese LLM.

These efforts reflect my commitment to practical, socially meaningful AI. My background in intelligent systems and NLP equips me to support this project with both theoretical depth and real-world application.

II. Current and Past Positions

- 2008 – 2018: Lecturer of the Faculty of Computer Science and Engineering

- 2008 – 2018: Head of Department of Software Engineering, Faculty of Computer Science and Engineering

- 2018 - 2025: Vice Dean of the Faculty of Computer Science and Engineering

- 2025 - Now: Dean of the Faculty of Computer Science and Engineering

III. Awards and Honors

- Outstanding Scientist with International Publications, Vietnam National University Ho Chi Minh City, 2024.

- Microsoft Accelerate Foundation Models Research (AMFR) - $60.000 USD

- Human and Algorithms for Detecting and Counter-attacking Fake Medical News - Collaborated with EPFL (Switzerland) - Funded by Nafosted (PI), 2021-2023

- Development of a Vietnamese- Bahnaric machine translation and Bahnaric text-to-speech system (all dialects) - KC-4.0-29/19-25 (PI) - funded by MOST (2021-2024)

- Development of an AI system for automatic machine translation and text-to-speech system for the Ba Na Kriem language - funded by Binh Dinh Province (2021-2024)

IV. Publications

Related publications:

- K. Ta Gia et al., “LoGoSAM: Enhancing Prototypical Networks for Medical Image One-Shot Segmentation Using Local-Global Encoder Integration and Visual Prompting,” Proc. 9th Int. Conf. Inf. Commun. Technol. Intell. Syst. (ICTIS), Thailand, 2025.

- G. D. Lu et al., “Unlocking the Potential: An Evaluation of Text-to-Speech Models for the Bahnar Language,” Proc. 8th IEEE/ACIS Int. Conf. Big Data, Cloud Comput., Data Sci. (BCD), Ho Chi Minh City, Vietnam, 2023.

- T. Q. Thanh et al., “BaNaVA: A Cross-Platform AI Mobile Application for Preserving the Bahnaric Languages,” Proc. 8th IEEE/ACIS Int. Conf. Big Data, Cloud Comput., Data Sci. (BCD), Ho Chi Minh City, Vietnam, 2023.

- N. T. V. Toan and T. Q. Thanh, “VLF-VQA: Vietnamese Lightweight Fusion Architecture for Visual Question Answering,” Proc. 13th Conf. Inf. Technol. Appl. (CITA), Danang, Vietnam, 2024.

- K. N. H. Vo et al., “Revitalizing Bahnar Language Through Neural Machine Translation: Challenges, Strategies, and Promising Outcomes,” Proc. 14th Symp. Educ. Adv. Artif. Intell. (EAAI-24), Vancouver, Canada, 2024.

Best publications:

- H. T. Phan et al., “XGA-Osteo: Towards XAI-Enabled Knee Osteoarthritis Diagnosis with Adversarial Learning,” Proc. 2024 Int. Joint Conf. Artif. Intell. (IJCAI), 2024.

- S. T. Truong et al., “Crossing Linguistic Horizons: Finetuning and Comprehensive Evaluation of Vietnamese Large Language Models,” Proc. 2024 Annu. Conf. North Amer. Chapter Assoc. Comput. Linguist. (NAACL-24), Mexico City, Mexico, 2024.

- K. M. Le et al., “LAMPAT: Low-Rank Adaptation for Multilingual Paraphrasing Using Adversarial Training,” Proc. 38th AAAI Conf. Artif. Intell. (AAAI-24), Canada, 2024.

- T. H. Phan et al., “DIKOApp: An AI-Based Diagnostic System for Knee Osteoarthritis,” J. Imaging Informat. Med., vol. 1, 2025, Q1.

- D. Q. Nguyen et al., “BeCaked: An Explainable Artificial Intelligence Model for COVID-19 Forecasting,” Sci. Rep., vol. 12, no. 7969, 2022.

V. Other projects and scholarships funded by VINIF

- Emerging Big Data/AI and IoTs/5G technologies for smart cities (Co-PI), Funded by Vingroup Innovation Foundation (VINIF) (2019-2022) - VINIF.2019.DA01
BIOGRAPHICAL SKETCH

## Name: Trinh Huu Tung

Position title: Director of Children's Hospital 2

Education/training

| Institution and location | Degree | Completion date | Field of study |
| --- | --- | --- | --- |
| University of Medicine and Pharmacy at Ho Chi Minh city | Bachelor of Medicine | 07/1992 | General Medicine |
| University of Medicine and Pharmacy at Ho Chi Minh city | Specialist level I doctor | 07/1999 | General Pediatric |
| University of Medicine and Pharmacy at Ho Chi Minh city | Specialist level II doctor | 07/2005 | Pediatric Cardiology |

I. Personal Statement

As Director of Children's Hospital 2 and a pediatric specialist with over 30 years of clinical and research experience, my focus has been advancing child health in Vietnam. My extensive research, including numerous publications and projects, covers diverse pediatric areas and utilizes strong quantitative and analytical skills. After recognizing the potential of AI, I am now interested in applying AI to improve treatment for children. I aim to leverage my deep pediatric knowledge and research skills to help team analyze problems and build AI, which can aid building efficient and effective therapy for speech and language problems in children.

II. Current and Past Positions

- 1992 - 2000: Doctor in Center for Pediatrics, Development and Health of Ho Chi Minh City at 14 Ly Tu Trong Street, Ben Nghe Ward, District 1, Ho Chi Minh City.

- 2000 - 2007: Cardiologist at Children's Hospital 2.

- 2008 - 2010: Deputy Head of General Planning Department at Children's Hospital 2.

- 2010 - 03/2015: Head of General Planning Department at Children’s Hospital 2.

- 03/2015 - 08/2017: Deputy Director of Children’s Hospital 2.

- 08/2017 - Now: Director of Children’s Hospital 2.

III. Awards and Honors

- 2011: The title of Distinguished Physician

IV. Publications

Relevant publications:

- Nguyen Tat, T., Vo Hoang-Thien, N., Nguyen Tat, D., Nguyen, P. H., Ho, L. T., Doan, D. H., Phan, D. T., Duong, Y. N., Nguyen, T. H., Nguyen, T. K., Dinh, H. T., Dinh, T. T., Pham, A. T., Do Chau, V., Trinh, T. H., and Vo Thanh, L., "Prognostic values of serum lactate-to-bicarbonate ratio and lactate for predicting 28-day in-hospital mortality in children with dengue shock syndrome," in Medicine, vol. 103, no. 17, pp. e38000, 2024.

- Vo, L. T., Do, V. C., Trinh, T. H., Vu, T., and Nguyen, T. T, "Combined therapeutic plasma exchange and continuous renal replacement therapy in children with dengue-associated acute liver failure and shock syndrome: single-center cohort from Vietnam," in Pediatric Critical Care Medicine, vol. 24, no. 10, pp. 818–828, 2023.

- Huynh, Q. T. V., Trinh, M. T. T., Doan, K. K., Ho, B. T., Shen, S. C., Trinh, T. H., Vo, T. H., Le, N. Q. K., and Nguyen, N. T. K., "The Distribution of Autoantibodies by Age Group in Children with Type 1 Diabetes versus Type 2 Diabetes in Southern Vietnam," in Journal of Clinical Medicine, vol. 12, no. 4, pp. 1420, 2023.

- Trinh, T. H., Nguyen, N. M., Lam, K. T., Pham, T. N., Vu, N. T., Truong, L. N. U., & Tran, V. Q., "Anorectal manometry findings in relation with long-term functional outcomes of the patients operated on for Hirschsprung’s disease compared to the reference-based population," in Pediatric Surgery International, vol. 39, no. 1, pp. 131, 2023.

- Nhan, L. N. T., Khanh, T. H., Hong, N. T. T., Van, H. M. T., Nhu, L. N. T., Ny, N. T. H., Nguyet, L. A., Thanh, T. T., Anh, N. T., Hang, V. T. T., Qui, P. T., Viet, H. L., Tung, T. H., Ha, D. Q., Tuan, H. M., Thwaites, G., Chau, N. V. V., Thwaites, L., Hung, N. T., van Doorn, H. R., … Tan, L. V., "Clinical, etiological and epidemiological investigations of hand, foot and mouth disease in southern Vietnam during 2015–2018," in PLoS neglected tropical diseases, vol. 14, no. 8, pp. e0008544, 2020.

Best publications

- Tùng, T. H. ., Phượng, N. T. N. ., Việt, T. Q. ., Hưng, T. V. ., Xuân, Đặng M. ., Hồng, D. T. ., and Anh, V. T. K., “Thực trạng điều trị và khả năng đáp ứng khám, điều trị bệnh nhân dị tật bẩm sinh tim tại bệnh viện Nhi Đồng 2 giai đoạn 2018 – 2023,” in Tạp Chí Y học Dự phòng, vol. 34, no. 5 Phụ bản, pp. 37–50, 2024.

- Huynh, Q. T. V., Ho, B. T., Le, N. Q. K., Trinh, T. H., Lam, L. H. T., Nguyen, N. T. K., and Huang, S.,  "Pathological brain lesions in girls with central precocious puberty at initial diagnosis in Southern Vietnam," in Annals of Pediatric Endocrinology & Metabolism, vol. 27, no. 2, pp. 105–112, 2022.

- Nguyen, T. T., Le, N. T., Nguyen, N. M., Do, V. C., Trinh, T. H., and Vo, L. T., "Clinical features and management of children with dengue-associated obstructive shock syndrome: A case report," in Medicine, vol. 101, no. 43, pp. e31322, 2022.

- Kamel, M. G., Nam, N. T., Han, N. H. B., El-Shabouny, A. E., Makram, A. E. M., Abd-Elhay, F. A. E., Dang, T. N., Hieu, N. L. T., Huong, V. T. Q., Tung, T. H. and Hirayama, K., "Post-dengue acute disseminated encephalomyelitis: a case report and meta-analysis," in PLoS neglected tropical diseases, vol. 11, no. 6, pp. e0005715, 2017.

- Phung, N. N., Dinh, Q. N., Trinh, T. H., and Tran, D. T., "Organ Dysfunction in Severe Dengue among Children in a Vietnamese Hospital.," in Systematic Reviews in Pharmacy, vol. 11, no. 2, 2020.

V. Other projects and scholarships funded by VINIF: None

BIOGRAPHICAL SKETCH

## Name: Pham Hoang Anh

Position title: Vice Dean of the Faculty of Computer Science and Engineering, Ho Chi Minh City University of Technology - VNU-HCM, Vietnam

Education/training

| Institution and location | Degree | Completion date | Field of study |
| --- | --- | --- | --- |
| Ho Chi Minh City University of Technology - VNU-HCM, Vietnam | Bachelor of Engineering | 04/2005 | Computer Science and Engineering |
| Myongji University, Korea | Master | 02/2010 | Communication Engineering |
| Myongji University, Korea | Doctor of Philosophy | 02/2014 | Information and Communication Engineering |

I. Personal Statement

I am well-suited to serve as a senior member of this project, particularly in leading the development of the hardware-assisted AI proxy device and overseeing system-level AI integration. My research focuses on deploying AI in distributed and edge environments—crucial for the proposed system’s performance in offline and resource-constrained clinical settings. For instance, my work on elastic resource allocation for distributed computing (IEEE TWC 2023) offers directly applicable techniques for running speech-processing models on localized devices.

I have also developed secure, privacy-preserving AI systems using decentralized and federated approaches. My contributions to FedChain (IEEE TSC 2023) and BlockRoam (IEEE TMC 2022) ensure robustness and compliance when handling sensitive data—skills essential for the clinician dashboard and mobile app managing children's health information. In parallel, my experience applying AI to real-world domains like education and mental health—such as in personalized vocabulary generation with LLMs—aligns closely with the design of adaptive therapy content for children. Together, my expertise in hardware-aware AI deployment, secure system architecture, and personalized applications makes me well-prepared for this project.

II. Current and Past Positions

- 03/2014 – 01/2024: Lecturer of the Faculty of Computer Science and Engineering

- 02/2025 - Now: Vice Dean of the Faculty of Computer Science and Engineering

III. Awards and Honors

IV. Publications

Relevant publications:

- Vo Ngoc Sang, Nguyen Ngoc Thanh Xuan, Pham Tan Phuoc, Pham Hoang Anh, “Beyond Textbooks: A Novel Workflow for Customized Vocabulary Sheet Generation with Large Language Models,” Lecture Notes on Data Engineering and Communications Technologies, vol. 230, pp. 208–220, 2024.

- Vo Ngoc Sang, Nguyen Ngoc Thanh Xuan, Pham Tan Phuoc, Nguyen Quoc Viet, Pham Hoang Anh, “Enhancing AI Chatbots for Mental Health Support: A Comprehensive Approach,” Lecture Notes in Computer Science, vol. 15431, p. 12, 2024.

- Xuan Ngoc-Thanh Nguyen, Sang Ngoc Vo, Hoang-Anh Pham, “Mental Chatbot Application Using Retrieval Augmented Generation,” Lecture Notes in Networks and Systems, vol. 23, pp. 363–375, 2024.

- Tran Huy, Vu Van Tien, Le Thanh Van, Huynh Tuong Nguyen, Pham Hoang Anh, “Leveraging Data Analytics to Investigate the Effectiveness of Flipped Classroom Models: A Case Study of Practical Programming Teaching,” Electronic Journal of e-Learning (EJEL), vol. 22, no. 9, pp. 144–162, 2024.

- Tien Vu-Van, Huy Tran, Duy Tran Ngoc Bao, Hoang-Anh Pham, Nguyen Huynh Tuong, “Applying Lecturer Expectation and Learning Retention to an Adaptive Learning System,” Lecture Notes on Data Engineering and Communications Technologies, vol. 148, pp. 68–77, 2022.

Best publications:

- Cong T. Nguyen, Diep N. Nguyen, Dinh Thai Hoang, Khoa Tran Phan, Dusit Niyato, Hoang-Anh Pham, Eryk Dutkiewicz, “Elastic Resource Allocation for Coded Distributed Computing over Heterogeneous Wireless Edge Networks,” IEEE Transactions on Wireless Communications, vol. 22, no. 4, pp. 2636–2649, 2023.

- Cong T. Nguyen, Dinh Thai Hoang, Diep N. Nguyen, Yong Xiao, Hoang-Anh Pham, Eryk Dutkiewicz, Nguyen Huynh Tuong, “FedChain: Secure Proof-of-Stake-based Framework for Federated-blockchain Systems,” IEEE Transactions on Services Computing, vol. 16, no. 4, pp. 2642–2656, 2023.

- Duc Phuc Nguyen, Khanh Hung Vu, Duc Dung Nguyen, Hoang-Anh Pham, “F2SRGAN: A Lightweight Approach Boosting Perceptual Quality in Single Image Super-Resolution via A Revised Fast Fourier Convolution,” IEEE Access, vol. 11, pp. 29062–29073, 2023.

- Hoai-Nam Nguyen, Hoang-Anh Pham, Nguyen Huynh Tuong, Duc-Hiep Nguyen, “Leveraging Blockchain to Enhance Digital Transformation in Small and Medium Enterprises: Challenges and A Proposed Framework,” IEEE Access, vol. 12, pp. 74961–74978, 2024.

- Cong T. Nguyen, Diep Nguyen, Hoang Thai Dinh, Hoang-Anh Pham, Nguyen Huynh-Tuong, Yong Xiao, Eryk Dutkiewicz, “BlockRoam: Blockchain-based Roaming Management System for Future Mobile Networks,” IEEE Transactions on Mobile Computing, vol. 21, no. 11, pp. 3880–3894, 2022.

V. Other projects and scholarships funded by VINIF

None

BIOGRAPHICAL SKETCH

## Name: Le Trong Nhan

Position title: Lecturer of the Faculty of Computer Science and Engineering, Ho Chi Minh City University of Technology - VNU-HCM, Vietnam

Education/training

| Institution and location | Degree | Completion date | Field of study |
| --- | --- | --- | --- |
| Ho Chi Minh City University of Technology - VNU-HCM, Vietnam | Bachelor of Engineering | 04/2008 | Information Technology |
| Ho Chi Minh City University of Technology - VNU-HCM, Vietnam | Master of Engineering | 04/2010 | Computer Science |
| Université Rennes 1, France | Doctor of Philosophy | 06/2014 | Information Technology - Electrical Engineering |

I. Personal Statement

I bring extensive experience in embedded systems, energy-efficient hardware design, and AI-integrated IoT platforms, making me well-suited to lead the hardware development for this project on AI-driven personalized therapy for children with speech and language disorders. Over the past decade, my work has focused on low-power wireless sensor networks, including energy-efficient MAC protocols (IEEE Sensors Journal, ACM JETC 2015) and supercapacitor-based autonomous sensing systems (IEEE TII 2014). These are directly relevant for developing real-time, low-latency AI proxy devices for clinicians. I also have strong expertise in hardware-software co-design for edge AI. My recent projects include GRU-based schedulers for smart lighting and predictive maintenance of solar-powered IoT devices (LNDECT 2024), both of which involved deploying AI in resource-constrained environments—key for running personalized therapy locally on devices.

Additional work on NB-IoT-based data acquisition, OCR systems (ATC 2024), and edge computing for WSNs (ICIot 2022) supports the project’s goals of on-device speech processing and secure data syncing. My earlier contributions on wake-up radio MAC protocols (IEEE/ACM ToN 2018) and reconfigurable antennas (IEEE Comm. Letters 2016) further demonstrate a commitment to adaptive, user-centric embedded design. Overall, my background in energy-aware, AI-enabled hardware systems will be vital to building the responsive and efficient infrastructure this project demands.

II. Current and Past Positions

- 01/2017 - Now: Lecturer of Faculty of Computer Science and Engineering, Ho Chi Minh City University of Technology - VNU-HCM, Vietnam

III. Awards and Honors

IV. Publications

Relevant publications:

- Trong Tin Nguyen, Dang Thi Vo, Xuan Loc Hoang, Cao Thang Trinh, Trong Nhan Le, and Thien An Nguyen, “Energy Efficient Scheduler based on GRU Model for Smart Street Light using NBIoT,” Lecture Notes on Data Engineering and Communications Technologies, vol. 229, pp. 119–130, 2024.

- Minh Tai Pham Nguyen, Minh Khue Phan Tran, and Trong Nhan Le, “An Efficient Configuration Based on Deep Learning Models for Predictive Maintenance of Solar-Powered IoT Devices,” Lecture Notes on Data Engineering and Communications Technologies, vol. 2, pp. 113–122, 2024.

- Minh Tai Pham Nguyen, Thanh Binh Bui Ngoc, Duy Nam Nguyen Quoc, Trong Nhan Le, Thi Hong Tran, Minh Khue Phan Tran, “The proposed one-stage detector for aerial scenario detection,” in Proc. Int. Symp. Inf. Commun. Technol. (SOICT), 2024.

- Phuc Ho Trong, Phuc Vinh Tran, Phat Nguyen Hong, Trong Nhan Le, “Automated Data Acquisition for Water Metering System Using Narrowband Internet of Things and Optical Character Recognition Engine,” Proc. Int. Conf. Adv. Technol. Commun. (ATC), 2024, pp. 1–12.

- Thien An Nguyen, Nhu Hung Huynh, Trong Nhan Le, “Edge computing for wireless sensor network,” in Proc. Int. Conf. Intelligence of Things, vol. 148, pp. 87–97, 2022.

Best publications:

- Trong Nhan Le, Alain Pegatoquet, Michele Magno, “A Wake-Up Radio-based MAC Protocol for Autonomous Wireless Sensor Networks,” IEEE/ACM Trans. Netw., pp. 1–15, 2018.

- Trong Nhan Le, Alain Pegatoquet, Olivier Berder, Olivier Sentieys, “Energy-efficient power manager and MAC protocol for multi-hop wireless sensor networks powered by periodic energy harvesting sources,” IEEE Sensors J., vol. 15, no. 12, pp. 7208–7220, Dec. 2015.

- Trong Nhan Le, Alain Pegatoquet, Olivier Sentieys, Olivier Berder, “Energy-neutral design framework for supercapacitor-based autonomous wireless sensor networks,” ACM J. Emerg. Technol. Comput. Syst. (JETC), vol. 12, no. 2, pp. 19:1–19:21, Aug. 2015.

- Andrea Castagnetti, Alain Pegatoquet, Trong Nhan Le, Michel Auguin, “A joint duty-cycle and transmission power management for energy harvesting WSN,” IEEE Trans. Ind. Inform., vol. 10, no. 2, pp. 928–936, May 2014.

- Trong Nhan Le, Alain Pegatoquet, Trinh Le Huy, Leonardo Lizzi, Fabien Ferrero, “Improving Energy Efficiency of Mobile WSN Using Reconfigurable Directional Antennas,” IEEE Commun. Lett., vol. 20, no. 6, pp. 1243–1246, June 2016.

V. Other projects and scholarships funded by VINIF: None

BIOGRAPHICAL SKETCH

## Name: Le Thanh Van

Position title: Lecturer of the Faculty of Computer Science and Engineering, Ho Chi Minh City University of Technology - VNU-HCM, Vietnam

Education/training

| Institution and location | Degree | Completion date | Field of study |
| --- | --- | --- | --- |
| Can Tho University | Bachelor of Engineering | 09/2003 | Information Technology |
| University Paris 8, France | Master | 09/2005 | Information Technology |
| Université de Lyon 1, France | Doctor of Philosophy | 05/2008 | Information Technology |

I. Personal Statement

With a strong research background in AI, adaptive systems, and educational technologies, I am well-positioned to lead the development of adaptive assessment tools for children with developmental speech and language disorders. My work on adaptive learning platforms—such as An Adaptive Testcase Recommendation System and Data Mining of Formative and Summative Assessments—demonstrates my ability to design personalized, behavior-driven AI systems, directly applicable to individualized speech therapy. I have also developed scalable AI architectures for heterogeneous data processing, as seen in HybridGCN and FLORUS, which are relevant for building an AI proxy device capable of real-time audio processing and feedback under hardware constraints. My experience in optimizing end-to-end systems (Low-Code Framework for Big Data, Siamese KG-LSTM) supports the efficient deployment of AI models on edge devices. In addition, my background in NLP—including multilingual modeling in HSUM-HC and domain-specific applications—will contribute to the development of language-aware tools tailored for Vietnamese children. My earlier work on distributed systems (Store-Carry-Forward Scheme for VANETs) further supports reliable communication between the proxy device and clinician software. Together, these contributions position me to lead the integration of efficient, adaptive, and clinically meaningful AI systems in this project.

II. Current and Past Positions

- 2003 – 2010: Lecturer at CanTho University Software Center

- 2010 – 2011: Lecturer at Can Tho University

- 2011 - Now: Lecturer of the Faculty of Computer Science and Engineering, Ho Chi Minh City University of Technology - VNU-HCM, Vietnam

III. Awards and Honors

IV. Publications

Relevant publications:

- Tien Vu-Van, Huy Tran, Thanh-Van Le, Hoang-Anh Pham, and Nguyen Huynh-Trong, "An Adaptive Testcase Recommendation System to Engage Students in Learning: A Practice Study in Fundamental Programming Courses," International Journal of Advanced Computer Science and Applications, vol. 14, no. 6, pp. 1101–1109, 2023.

- Huy Tran, Tien Vu-Van, Tam Bang, Thanh-Van Le, Hoang-Anh Pham, and Nguyen Huynh-Tuong, "Data Mining of Formative and Summative Assessments for Improving Teaching Materials towards Adaptive Learning: A Case Study of Programming Courses at the University Level," Electronics, vol. 12, no. 14, pp. 1–17, 2023.

- Nguyen Doan Nhat Minh, Vu Dang Khoa, Vu Van Tien, Tran Huy, Le Thanh Van, Pham Hoang Anh, and Huynh Tuong Nguyen, "An Evaluation of Testcase Recommendation Systems Through Feedback Model," Lecture Notes in Networks and Systems, vol. 23, pp. 661–672, 2024.

- Son-Tin Nguyen, Dinh-Tuan Nguyen, and Thanh-Van Le, "Leveraging NLP for Multilingual Support in Academic Regulations," Communications in Computer and Information Science, vol. 2191, pp. 304–312, 2024.

- Truc D.T. Nguyen, Thanh-Van Le, and Hoang-Anh Pham, "Novel Store-Carry-Forward Scheme for Message Dissemination in Vehicular Ad-hoc Networks," ICT Express, vol. 3, no. 4, pp. 193–198, 2017.

Best publications:

- Dang-Anh-Khoa Nguyen, Sang Kha, and Thanh-Van Le, "HybridGCN: An Integrative Model for Scalable Recommender Systems with Knowledge Graph and Graph Neural Networks," International Journal of Advanced Computer Science and Applications, vol. 15, no. 5, pp. 1327–1337, 2024.

- Hong-Phuc Vo, Khoa-Gia-Cat Nguyen, and Thanh-Van Le, "FLORUS: An Efficient Big Data Framework for Telecom Customer Behavior Analysis," SN Computer Science, vol. 5, pp. 1–18, 2024.

- Phuoc-Minh Phan, Quoc-Hung-Thinh Luu, Tan-Loc Huynh, and Thanh-Van Le, "A More Refined Advancement to the Low-Code Framework for End-to-End Big Data Management," Lecture Notes on Data Engineering and Communications Technologies, vol. 229, pp. 73–84, 2024.

- Tri Cong-Toan Tran, Thien Phu Nguyen, and Thanh-Van Le, "HSUM-HC: Integrating BERT-Based Hidden Aggregation to Hierarchical Classifier for Vietnamese Aspect-Based Sentiment Analysis," Proceedings of the 8th NAFOSTED Conference on Information and Computer Science (NICS), Hanoi, Vietnam, 2022.

- Tien T. T. Tran, Sy V. Nghiem, Van T. Le, Tho T. Quan, Vinh Nguyen, Hong Yung Yip, and Olivier Bodenreider, "Siamese KG-LSTM: A Deep Learning Model for Enriching UMLS Metathesaurus Synonymy," The 12th IEEE International Conference on Knowledge and Systems Engineering (KSE), Can Tho, Vietnam, 2020.

V. Other projects and scholarships funded by VINIF: None

BIOGRAPHICAL SKETCH

## Name: Ha Thi Thanh Huong

Position title: Head of Department of Tissue Engineering and Regenerative Medicine

Education/training

| Institution and location | Degree | Completion date | Field of study |
| --- | --- | --- | --- |
| University of Science - VNU-HCM | Bachelor | 10/2011 | Medical Biotechnology |
| Stanford University | Doctor of Philosophy | 08/2018 | Neuroscience |

I. Personal Statement

As a senior member of this project, I bring a strong interdisciplinary background in neuroscience, AI, and cognitive assessment, with a focus on personalized diagnostics and intervention. My work includes AI models for Alzheimer’s diagnosis using ensemble and XG-Boost methods (IBRO Neuroscience Reports 2022; Biomedical Research and Therapy 2023), and culturally adapted cognitive assessments for Vietnamese populations (The Clinical Neuropsychologist 2023). I have also led research on plasma biomarkers (Frontiers in Molecular Neuroscience 2023), brain atrophy-based clustering (Brain Multiphysics 2024), and EEG analysis of behavioral interventions (IBRO Neuroscience Reports 2023), all of which inform personalized, neuro-informed therapy. These experiences position me to support the project’s development of adaptive assessment and treatment tools for children with speech and language disorders.

II. Current and Past Positions

10/2018 –  09/2020: Lecturer of Faculty of Biomedical engineering, International University - Vietnam National University Ho Chi Minh City

09/2020 – Now: Head of Faculty of Biomedical engineering, International University - Vietnam National University Ho Chi Minh City

III. Awards and Honors

| Awards / Hornors | Issuing organization | Year |
| --- | --- | --- |
| National Golden Globe Award, Medical Technology | Decision no.: 514 -QĐKT/TWĐTN-VP | 2023 |
| National Outstanding Teacher Title | Minister of Education and Training | 2023 |
| Certificate of Merit, Creative Youth Badge | Central Standing Committee of Ho Chi Minh Communist Youth Union | 2023 |
| Early Career Award | International Brain Research Organization | 2020 |

IV. Publications

Relevant publications:

- Thanh Truc-Quynh Nguyen, Chau Bao Dinh Hoang, Minh Dung Hoang Le, Ngoc Tram Anh V, Halle Quang, Christopher Minh Nguyen, Claire Goodman, George M Savva, Van Luan Pham, Trung Thu Tran, Van Toi Vo, and Thi Thanh Huong Ha, "Assessing cognitive decline in Vietnamese older adults using the Montreal Cognitive Assessment-Basic (MoCA-B) and Informant Questionnaire on Cognitive Decline in the Elderly (IQCODE) during the COVID-19 pandemic: a feasibility study," in The Clinical Neuropsychologist, vol. 37, no. 5, pp. 1043–1061, 2023.

- Dong Nguyen, Hoang Nguyen, Hong Ong Hoang Le, Huong Ha, Nguyen Thanh Duc, and Hoan Thanh Ngo, "Ensemble learning using traditional machine learning and deep neural network for diagnosis of Alzheimer’s disease," in IBRO Neuroscience Reports, vol. 13, pp. 255–263, 2022.

- Linh Ha Chu, Chi Que Chau, Nidal Kamel, Huong Ha,  and Norashikin Yahya, "Functional excitation-inhibition ratio for social anxiety analysis and severity assessment," in Frontiers in Psychiatry, vol. 15, pp. 1461290, 2024.

- My Nguyen, Bao Pham, Toi Vo, and Huong Ha, "Revealing the heterogeneity of plasma protein and cognitive decline trajectory among Mild Cognitive Impairment patients by clustering of brain atrophy features," in Brain Multiphysics, vol. 6, pp. 100093, 2024.

- Hiep Do, Huy Hoang, Nghia Nguyen, Anh An, Huy Chau, Quang Khuu, Luan Tran, Thao Le, Anh Le, Kien Nguyen, Toi Vo, and Huong Ha, "Intermediate effects of mindfulness practice on the brain activity of college students: An EEG study," in IBRO Neuroscience Reports, vol. 14, pp. 308–319, 2023.

Best publications:

- Huong, Ha, et al., "Shank and zinc mediate an AMPA receptor subunit switch in developing neurons," in Frontiers in molecular neuroscience, vol. 11, pp. 405, 2018.

- Thien Hoang Minh Cao, Anh Phuc Hoang Le, Tai Tien Tran, …, and Huong Thi Thanh Ha, "Plasma cell-free RNA profiling of Vietnamese Alzheimer's patients reveals a linkage with chronic inflammation and apoptosis: a pilot study," in Frontiers in Molecular Neuroscience, vol. 16, pp. 1308610, 2023.

- My Nguyen, Bao Pham, Toi Vo, and Huong Ha, "Revealing the heterogeneity of plasma protein and cognitive decline trajectory among Mild Cognitive Impairment patients by clustering of brain atrophy features," in Brain Multiphysics, vol. 6, pp. 100093, 2024.

- Khoi Nguyen, My Nguyen, Khiet Dang, Bao Pham, Vy Huynh, Toi Vo, Lua Ngo, and Huong Ha, "Early Alzheimer’s disease diagnosis using an XG-Boost model applied to MRI images," in Biomedical Research and Therapy, vol. 10, no. 9, pp. 5896–5911, 2023.

- Anh Phuc Hoang Le, Quang Lam Nguyen, Bao Hoai Pham, Thien Hoang Minh Cao, Toi Van Vo, Khon Huynh, and Huong Thi Thanh Ha, "SALAD: syringe-based arduino-operated low-cost antibody dispenser," in HardwareX, vol. 15, pp. e00455, 2023.

V. Other projects and scholarships funded by VINIF

None

BIOGRAPHICAL SKETCH

## Name: Ngo Thi Lua

Position title: Lecturer of the Faculty of Biomedical Engineering, International University - Vietnam National University Ho Chi Minh City

Education/training

| Institution and location | Degree | Completion date | Field of study |
| --- | --- | --- | --- |
| Ho Chi Minh City University of Technology - VNU-HCM, Vietnam | Bachelor of Engineering | 10/2009 | Electronics and Telecommunication Engineering |
| Ho Chi Minh City University of Technology - VNU-HCM, Vietnam | Master of Engineering | 02/2012 | Electronics and Telecommunication Engineering |
| Korea University | Doctor of Philosophy | 02/2020 | Neuroscience and Cognitive Engineering |

I. Personal Statement

With a strong track record in applying AI to healthcare and biomedical challenges, I am well-prepared to serve as a senior member of this project on personalized therapy and assessment for developmental language and speech sound disorders in children. My research spans AI-driven frameworks for mental health, neuroimaging, and assistive technologies, demonstrating both technical depth and interdisciplinary collaboration.

Notably, my recent work on EEG-based detection of mental disorders (Neuroscience Research Notes, 2025) highlights how multimodal neural data can reveal complex cognitive patterns. I have also co-developed AI systems for sleep-stage scoring and lifestyle-informed sleep disorder classification, which align with behavioral monitoring in children.

In addition, I have built brain-computer interfaces for motor-impaired users and deep learning models for neurodegenerative disease diagnosis—both involving biosignal processing and personalized feedback loops. My earlier work on retinal layer segmentation in OCT images (IEEE T-IP and Electronics Letters) and recent efforts on MRI-based Alzheimer’s detection and brain tumor segmentation further demonstrate my ability to lead technical development in medical AI. Collectively, these experiences position me to contribute meaningfully to the AI design, data integration, and clinical evaluation aspects of this project.

II. Current and Past Positions

07/2020 –  Now: Lecturer of the Faculty of Biomedical Engineering, International University - Vietnam National University Ho Chi Minh City

III. Awards and Honors

| No. | Awards / Honors | Issuing organization | Year |
| --- | --- | --- | --- |
| 1 | Second Prize of Ho Chi Minh City Innovation Award | People's Committee of Ho Chi Minh City | 2021 |
| 2 | Encouragement Prize of the HCMC Artificial Intelligence Application Innovation Project Competition | Department of Science and Technology of Ho Chi Minh City | 2020 |

IV. Publications

Relevant publications:

- L. Ngo, A. Le, K. Ho, T. Le, N. Nguyen, S. Nguyen, D. Duong, and H. Ha, “Electroencephalogram (EEG) based automated detection of mental disorders using artificial intelligence processing pipelines,” Neuroscience Research Notes, 2025.

- T. Luu, A. Dang-Hieu, T. Ly, H. P. Thanh, H. Ha, and L. Ngo, “Developing a photoplethysmography-based automated sleep-stage scoring framework using artificial intelligence,” in Proc. 10th Int. Conf. Vietnam Dev. Biomed. Eng., 2023.

- A. Le, G. Truong, H. Hoang, and L. Ngo, “Developing the automated classification of sleep disorders based on lifestyle factors,” in Proc. 10th Int. Conf. Vietnam Dev. Biomed. Eng., 2023.

- T.-H. Nguyen, P.-D. Sam, L. Ngo, and H.-D. Nguyen, “Thinking-Computer Control System (TCCS) for remotely controlling electronic devices by brainwaves – An assistive BCI system for people with motor-impaired disabilities,” in Proc. 10th Int. Conf. Vietnam Dev. Biomed. Eng., 2023.

- V. Q. Tran, N. Trung-Tin, B. Thuan, B. Trung-Tin, N. T. Hoan, L. Ngo, “Classification of Alzheimer’s diseases MRI brain images leveraging 3D convolutional neural networks,” in Proc. 9th Int. Conf. Vietnam Dev. Biomed. Eng., pp. 462–478, 2023.

Best publications:

- L. Ngo, J. Cha, and J. H. Han, “Deep neural network regression for automated retinal layer segmentation in optical coherence tomography images,” IEEE Trans. Image Process., vol. 29, pp. 303–312, 2020.

- L. Ngo and J. H. Han, “Multi-level deep neural network for efficient segmentation of blood vessels in fundus images,” Electron. Lett., vol. 53, no. 16, pp. 1096–1098, 2017.

- K. Dang, V. V. Toi, L. Ngo, and H. T. T. Ha, “A deep learning framework integrating MRI image preprocessing methods for brain tumor segmentation and classification,” IBRO Neurosci. Rep., vol. 13, pp. 523–532, 2022.

- K. Nguyen, M. Nguyen, K. Dang, B. Pham, V. Huynh, T. Vo, L. Ngo, and H. Ha, “Early Alzheimer’s disease diagnosis using an XG-Boost model applied to MRI images,” Biomed. Res. Ther., vol. 10, no. 9, pp. 5896–5911, 2023.

- L. Ngo and J. H. Han, “Graph-based segmentation with homogeneous hue and texture vertices,” Opt. Appl., vol. 51, no. 1, 2021.

V. Other projects and scholarships funded by VINIF: None

BIOGRAPHICAL SKETCH

## Name: Huynh Kim Phat

Position title: Assistant Professor of Industrial and Systems Engineering Department at North Carolina A&T State University.

Education/training

| Institution and location | Degree | Completion date | Field of study |
| --- | --- | --- | --- |
| International University – Vietnam National University – Ho Chi Minh | BSc | 08/2018 | Biomedical Engineering |
| North Dakota State University | M.S | 05/2022 | Industrial Engineering and Management |
| University of South Florida | Ph.D. | 12/2023 | Industrial Engineering |

I. Personal Statement

I have a strong background in developing and deploying AI-driven methods for health monitoring, data-driven modeling, and sensor-based analytics. Throughout my academic journey in Biomedical Engineering and Industrial Engineering, I have focused on integrating domain knowledge with advanced machine learning techniques to address complex healthcare challenges—from modeling hospital-acquired infection risk to creating real-time diagnostic tools using multimodal data. My work demonstrates expertise in designing systems that fuse disparate data sources (e.g., audio signals, physiological metrics) for richer clinical insight, a core requirement for advancing speech and language therapy through AI. Equally important, my experience leading interdisciplinary research teams and mentoring students in sensor integration and robust decision-making strategies has prepared me to collaborate effectively with clinicians, computer scientists, and other stakeholders. I have spearheaded projects involving hardware-software integration, wearable devices, and AI algorithms to improve patient outcomes, ensuring that models are grounded in both clinical realities and technical feasibility. These experiences directly translate to the proposed endeavor, where I will help build and optimize AI-driven solutions for personalized therapy and efficient progress tracking in children with speech and language disorders.

II. Current and Past Positions

- 2024-Present: Assistant Professor of Industrial and Systems Engineering – North Carolina A&T State University, USA

- 2023-2024: Postdoctoral Researcher & Adjunct Professor of Industrial and Management Systems Engineering – University of South Florida, USA

III. Awards and Honors

I have been honored with multiple awards recognizing the quality and impact of my research in reliability and maintainability. These include the IISE Quality Control and Reliability Engineering (QCRE) Division William A. Golomski Award for outstanding papers at the 71st and 69th Annual Reliability and Maintainability Symposium (RAMS) in 2025 and 2023, respectively. I also received the Stan Oftshun Award for the best paper by students of an SRE member at the 70th RAMS Conference in 2024, the Thomas L. Fagan, Jr. Award for best student paper at the 69th RAMS Conference in 2023, and the Doug Ogden Award for the best technical paper authored by an SRE member at the same conference.

IV. Publications

Five relevant publications: († = Corresponding author, S = Students, * = Co-first)

- Huynh, P. K., Setty, A., Phan, H., & Le, T. Q. (2021). Probabilistic domain-knowledge modeling of disorder pathogenesis for dynamics forecasting of acute onset. Artificial intelligence in medicine, 115, 102056.

- Nguyen, D.S, Le, M. H. N.S, Le, T. Q., Charles-Okezie, C., Diaz, M. J., ... & Huynh, P. K.†. (2024). Deep Learning-based Integrated System for Intraoperative Blood Loss Quantification in Surgical Sponges. IEEE Journal of Biomedical and Health Informatics.

- Huynh, P. K.; Nguyen, D.; Binder, G.; Ambardar, S.; Le, T. Q.; Voronine, D. V. (2023). Multifractality in Surface Potential for Cancer Diagnosis. The Journal of Physical Chemistry B 2023, 127, 6867-6877.

- Huynh, P. K., Setty, A. R., Le, T. B., & Le, T. Q. (2022). A noise-robust Koopman spectral analysis of an intermittent dynamics method for complex systems: a case study in pathophysiological processes of obstructive sleep apnea. IISE Transactions on Healthcare Systems Engineering, 1-16.

- Huynh, P. K., Setty, A. R., Tran, Q. M., Yadav, O. P., Yodo, N., & Le, T. Q. (2022). A domain-knowledge modeling of hospital-acquired infection risk in healthcare personnel from retrospective observational data: A case study for COVID-19. Plos one, 17(11).

Five other publications

- Huynh, P. K.*, Singh, P.*, Nguyen, D., Le, T. Q., & Moreno, W. (2024). Leveraging Multi-Criteria Integer Programming Optimization for Effective Team Formation. IEEE Transactions on Learning Technologies.

- Le, T. Q., Huynh, P. K., & Tomaselli, L. (2023). Navigating the night: evaluating and accessing wearable sleep trackers for clinical use. Sleep.

- Nguyen, T. T., Kasperski, D., Huynh, P. K., Le, T. Q., & Le, T. B. (2025). Modal analysis of blood flows in saccular aneurysms. Physics of Fluids, 37(1).

- Huynh, P. K., Irish, L., Yadav, O. P., Setty, A., & Le, T. Q. (2022, January). Causal Inference in Longitudinal Studies Using Causal Bayesian Network with Latent Variables. 2022 Annual Reliability and Maintainability Symposium (RAMS) (pp. 1-7). IEEE.

- Huynh, P. K. *, Bui, C. T. *, Phan, H. T., Le, T. Q., & Van Toi, V. (2018, June). Developing Neural-fuzzy-based Unscented Kalman Filter Algorithm for Atrial Fibrillation Onset Prediction. In International Conference on the Development of Biomedical Engineering in Vietnam (pp. 119-125). Springer, Singapore.

V. Other projects and scholarships funded by VINIF: None

BIOGRAPHICAL SKETCH

## Name: Nguyen Thanh Sang

Position title: Head of the Department of  Interdisciplinary Clinical Psychology – Rehabilitation – Traditional Medicine at Children's Hospital 2

Education/training

| Institution and location | Degree (if applicable) | Completion date (mm/yyyy) | Field of study |
| --- | --- | --- | --- |
| Guangxi Traditional Chinese Medical University | Bachelor | 07/2009 | Traditional medicine |
| Vietnam University Of Traditional Medicine | Master | 06/2013 | Traditional medicine |
| University of Medicine and Pharmacy Ho Chi Minh city | Specialist Level II Doctor | 12/2020 | Traditional medicine |

I. Personal Statement

In my current role as Head of the Department of  Interdisciplinary Clinical Psychology – Rehabilitation – Traditional Medicine at Children's Hospital 2, I am committed to integrating advanced technologies, particularly artificial intelligence (AI), into pediatric clinical practice. As language and speech disorders in young children become increasingly prevalent and complex, there is a growing need for innovative, personalized, and scalable treatment approaches. AI offers promising solutions to enhance early diagnosis, tailor interventions, and objectively assess therapeutic outcomes.

My first responsibility is to facilitate access to an appropriate and diverse sample of pediatric patients for the study. Our department serves a large number of children with language and speech disorders, making it a valuable source for patient recruitment that aligns with the research criteria. I ensure that the selection process follows ethical guidelines and supports the study's objectives.

Secondly, I act as a bridge between departments involved in the project, including Speech and Language Therapy, Psychology, Pediatrics, Radiology, and IT. This role involves promoting smooth communication, coordinating schedules, and ensuring data sharing and integration across units—all of which are essential for the success of a multidisciplinary, AI-based study.

Lastly, I contribute expert insights based on clinical experience to refine the research design, patient assessment protocols, and therapeutic approaches. My feedback helps align AI applications with real-world clinical needs, improving the study's relevance and impact.

Through these responsibilities, I support the development of an innovative, patient-centered model for diagnosing and treating language and speech sound disorders using AI, while reinforcing interdepartmental collaboration within the hospital.

II. Current and Past Positions

- 11/2011 – 06/2014: General Practitioner, Outpatient Department at Saigon General Hospital

- 07/2014 – 11/2023: Deputy Head, Department of Rehabilitation at Le Van Thinh Hospital

- 11/2023 – Present: Head, Department of Interdisciplinary Clinical Psychology – Rehabilitation – Traditional Medicine at Children's Hospital 2

III. Awards and Honors

- 2018 – Outstanding Achievement Award, presented by the Ho Chi Minh City Department of Health for exemplary performance in the healthcare sector

- 2020 – Outstanding Achievement Award, presented by the Ho Chi Minh City Department of Health for exemplary performance in the healthcare sector

- 2021 – Outstanding Achievement Award, presented by the Ho Chi Minh City Department of Health for exemplary performance in the healthcare sector

- 2022 – Outstanding Performance Commendation, awarded by the Chairman of Ho Chi Minh City

IV. Publications

- 2018 – Effectiveness of Therapeutic Ultrasound on Patients with Carpal Tunnel Syndrome. Journal of Ho Chi Minh City Medicine, Vol. 22(S2), pp. 316–320.

- 2020 – Comparison of Pain Relief Effects Between Laser Acupuncture and Therapeutic Ultrasound in Patients with Carpal Tunnel Syndrome, pp. 113–119.

- 2022 – The Impact of COVID-19 on the Psychological Health of Pregnant Women. Vietnam Journal of Psychology, No. 7, 2022.

V. Other projects and scholarships funded by VINIF

None

BIOGRAPHICAL SKETCH

## Name: Nguyen Chau Tuyet Nhu

Position title: Staff of Psychology - Rehabilitation Department

Education/training

| Institution and location | Degree (if applicable) | Completion date (mm/yyyy) | Field of study |
| --- | --- | --- | --- |
| University of Medicine and Pharmacy Ho Chi Minh city | Bachelor | 07/2010 | Physiotherapy |
| Pham Ngoc Thach Medical University | Certificate | 09/2014 | Speech therapy |
| University of Medicine and Pharmacy Ho Chi Minh city | Master | 08/2023 | Rehabilitation techniques |

I. Personal Statement

I have worked with related communication disorders like autism spectrum disorder, language disorder, and speech sound disorder for 12 years. For me, my daily tasks include evaluating kids, creating intervention plans, and assisting parents. Additionally, I teach a module in Pham Ngoc Thach University of Medicine's speech therapy course.

Between the ages of 0 and 3, children begin to acquire their first language and speech interaction skills. If the child's language delay persists after the age of three, it indicates that the delay is still present. However, to analyze and plan the language or speech components in which the child is delayed and requires assistance, Speech Therapists must have extensive clinical experience and a thorough understanding of the developmental milestones of language and speech. I will work with the research subjects in this study as a clinician. I'll help by describing the normal speech and language patterns of young children between the ages of three and six. I will help with the analysis of unusual language and speech patterns. Lastly, I'll create intervention strategies and track the kids' development.

II. Current and Past Positions

- 04/2018 - Now: I served as a guest lecturer in Speech Therapy at Pham Ngoc Thach University of Medicine. Teaching 10-month Pediatric Speech Therapy courses and 3-month Speech Therapy courses to children with autism spectrum disorders.

- 04/2018 - Now: Served as a clinical practice lecturer in speech therapy at Children's Hospital 2 since April 2018. Supervising clinical practice of 9-month and 3-month pediatric speech therapy students based on topics at Children's Hospital 2.

- 10/2020 - 04/2021: Provided speech therapy support to children in Tay Ninh, Binh Phuoc, and Dong Nai provinces through the Center for Sustainable Health Development - VietHealth

- 01/2021 - Now: In charge of speech therapy at Children's Hospital 2

III. Awards and Honors

- Pham Ngoc Thach University of Medicine awarded a certificate of merit for "Excellence in training in Speech Therapy and Speech Therapy Intervention."

- Ho Chi Minh City Department of Health Certificate of Merit for Outstanding Mission Completion.

IV. Publications

None

V. Other projects and scholarships funded by VINIF

None

BIOGRAPHICAL SKETCH

## Name: Nguyen Quang Duc

Position title: Teaching Assistant in the Faculty of Computer Science and Engineering, Ho Chi Minh City University of Technology - VNU-HCM, Vietnam

Education/training

| Institution and location | Degree (if applicable) | Completion date (mm/yyyy) | Field of study |
| --- | --- | --- | --- |
| Ho Chi Minh City University of Technology - VNU-HCM, Vietnam | Bachelor of Engineering | 06/2022 | Computer Science |
| Ho Chi Minh City University of Technology - VNU-HCM, Vietnam | Master of Engineering | 01/2025 | Computer Science |

I. Personal Statement

With a strong background in AI and its applications to healthcare and linguistically complex settings, I am well-positioned to lead this project on AI-assisted speech and language therapy for children in Vietnam. My research focuses on developing theoretically grounded and practically impactful AI systems for healthcare, education, and low-resource languages. Notably, my work on Crossing Linguistic Horizons showcases expertise in adapting large language models (LLMs) for Vietnamese—critical for building culturally appropriate speech therapy tools.

In addition, my work on nonmyopic Bayesian optimization and adaptive decision-making systems directly supports personalized therapy and real-time progress tracking. My broader expertise in generative models, explainable AI, and multimodal learning—applied to drug design, subgraph matching, and voice conversion—enables sophisticated modeling of children's speech and therapeutic simulations. My commitment to trustworthy AI ensures that tools developed will be transparent and clinically reliable. Finally, my interdisciplinary collaborations and top-tier publications demonstrate my ability to lead impactful, cross-cutting AI research.

II. Current and Past Positions

- 2023 – Present: Teaching Assistant of the Faculty of Computer Science and Engineering

III. Awards and Honors

- Microsoft Accelerate Foundation Models Research (AMFR) - $60.000 USD

- Master's, PhD Scholarship Programme of Vingroup Innovation Foundation (VINIF)

IV. Publications

Relevant publications:

- Sang T. Truong, Duc Q. Nguyen, Willie Neiswanger, Ryan-Rhys Griffiths, Stefano Ermon, Nick Haber, Sanmi Koyejo, “Nonmyopic Bayesian Optimization in Dynamic Cost Settings,” in ICLR Workshop on Agentic AI for Science: Hypothesis Generation, Comprehension, Quantification, and Validation, 2025.

- Sang T. Truong*, Duc Q. Nguyen*, Toan Nguyen*, Dong D. Le*, Nhi N. Truong*, Tho Quan, Sanmi Koyejo, “Crossing Linguistic Horizons: Finetuning and Comprehensive Evaluation of Vietnamese Large Language Models,” in Proceedings of The 2024 Annual Conference of the North American Chapter of the Association for Computational Linguistics, 2024.

- Sang T. Truong, Duc Q. Nguyen, Tho Quan, Sanmi Koyejo, “Thomas: Learning to Explore Human Preference via Probabilistic Reward Model,” in ICML Workshop: The Many Facets of Preference-Based Learning (MFPL), 2023.

- Dang Tran Dat, Tang Quoc Thai, Duc Q. Nguyen, Vo Duy Hung, and Quan Thanh Tho, “Voice Conversion for Natural-Sounding Speech Generation on Low-Resource Languages: A Case Study of Bahnaric,” in Proceedings of the 2nd International Conference on Intelligence of Things (ICIT 2023), 2023.

- Duc Nguyen, Thien Pham, and Tho Quan, “Design, implementation and evaluation for a high precision prosthetic hand using MyoBand and Random Forest algorithm,” Science & Technology Development Journal - Engineering and Technology, vol. 3, pp. 28-39, 2020.

Best publications:

- Sang T. Truong*, Duc Q. Nguyen*, Toan Nguyen*, Dong D. Le*, Nhi N. Truong*, Tho Quan, Sanmi Koyejo, “Crossing Linguistic Horizons: Finetuning and Comprehensive Evaluation of Vietnamese Large Language Models,” in Proceedings of The 2024 Annual Conference of the North American Chapter of the Association for Computational Linguistics, 2024.

- Thanh Toan Nguyen, Quang Duc Nguyen, Zhao Ren, Jun Jo, Quoc Viet Hung Nguyen, Thanh Tam Nguyen, “10X Faster Subgraph Matching: Dual Matching Networks with Interleaved Diffusion Attention,” In Proceedings of 2023 International Joint Conference on Neural Networks (IJCNN), 2023.

- Duc Q. Nguyen, Khoan D. Le, Bach T. Ly, An D. Nguyen, Quang H. Nguyen, Tuan H. Nguyen, Cuong Quoc Duong, Thanh N. Truong, Phuong Thuy Viet Nguyen, Tho T. Quan, “Towards de Novo Drug Design for the Coronavirus: A Drug-Target Interaction Prediction Approach Using Atom-Enhanced Graph Neural Network with Multi-Hop Gating Mechanism,” In Proceedings of 9th NAFOSTED Conference on Information and Computer Science (NICS), 2022.

- Duc Q. Nguyen, Thanh Toan Nguyen, Jun Jo, Florent Poux, Shikha Anirban, Tho Quan, “Explainable Neural Subgraph Matching with Learnable Multi-hop Attention,” IEEE Access (Q1), 2024

- Duc Q. Nguyen, Nghia Q. Vo, Thinh T. Nguyen, Khuong A. Nguyen, Quang H. Nguyen, Dang N. Tran, and Tho T. Quan, “BeCaked: An Explainable Artificial Intelligence Model For COVID-19 Forecasting,” Scientific Reports (Q1), vol. 12, no. 7969, 2022.

V. Other projects and scholarships funded by VINIF

- Master’s and Ph.D. Scholarship Programme of Vingroup Innovation Foundation (VINIF) under Grant VINIF.2022.ThS.023

BIOGRAPHICAL SKETCH

## Name: Vu Nguyen Minh Duc

Position title: Master’s student of the Faculty of Biomedical Engineering at International University - Vietnam National University - Ho Chi Minh

Education/training (Begin with baccalaureate or other initial professional education. Add/delete rows if necessary.)

| Institution and location | Degree (if applicable) | Completion date (mm/yyyy) | Field of study |
| --- | --- | --- | --- |
| University of Medicine and Pharmacy at Ho Chi Minh city | Bachelor | 08/2022 | Physiotherapy |

I. Personal Statement

I am currently pursuing a master's degree in Biomedical Engineering at International University - VNU-HCMC, driven by a passion for computational neuroscience and the application of AI in healthcare. My foundational background is in rehabilitation techniques, and I previously worked as a physiotherapist at the city children's hospital. This role provided me with valuable experience interacting with pediatric patients, including those with speech sound and developmental language disorders. I am eager to integrate this practical clinical understanding with my current engineering studies to contribute to developing effective AI-driven solutions for improving assessment and intervention for children with these communication challenges.

II. Current and Past Positions

- 2022-2024: Physiotherapist at City Children's Hospital.

- 2025–Present: Master’s student of the Faculty of Biomedical Engineering at International University - Vietnam National University - Ho Chi Minh.

III. Awards and Honors

None

IV. Publications

None

V. Other projects and scholarships funded by VINIF

None

BIOGRAPHICAL SKETCH

## Name: Nguyen Thi Dieu Linh

Position title: Speech therapist at Children's Hospital 2

Education/training (Begin with baccalaureate or other initial professional education. Add/delete rows if necessary.)

| Institution and location | Degree (if applicable) | Completion date (mm/yyyy) | Field of study |
| --- | --- | --- | --- |
| University of Medicine and Pharmacy at Ho Chi Minh city | Bachelor | 08/2022 | Physiotherapy |
| Pham Ngoc Thach Medical University | Certificate | 03/2025 | Speech Therapy |

I. Personal Statement

As a speech therapist at Children’s Hospital 2, I work directly with many children aged 3-6 who have developmental language and speech sound disorders. This helps me understand their needs and how therapy can be more helpful. I believe my experience will support the project by giving practical ideas for how AI can be used to make therapy more personalized and to check how well it working.

II. Current and Past Positions

2022 - Now: Working at  Children’s Hospital 2 as a physical therapist and speech therapist

III. Awards and Honors

None

IV. Publications

None

V. Other projects and scholarships funded by VINIF

None

BIOGRAPHICAL SKETCH

## Name: Nguyen Ngoc Tuong Vy

Position title: Speech therapist at Children's Hospital 2

Education/training (Begin with baccalaureate or other initial professional education. Add/delete rows if necessary.)

| Institution and location | Degree (if applicable) | Completion date (mm/yyyy) | Field of study |
| --- | --- | --- | --- |
| University of Medicine and Pharmacy at Ho Chi Minh city | Bachelor | 08/2022 | Physiotherapy |
| Pham Ngoc Thach Medical University | Certificate | 05/2025 | Speech therapy |

I. Personal Statement

I hold a Bachelor's degree in Physical Therapy and am currently a student in Speech-Language Therapy, with my experience working with children at Children's Hospital 2.  In this project, I will primarily be involved in data collection, therapy implementation, and behavioral observation for children aged 3 to 6. I will directly conduct assessments and provide personalized interventions, creating a supportive environment that encourages communication. I will also collaborate with the technical team to provide insights into child behavior and therapy progress, helping to adjust AI models for optimizing treatment plans. This project will offer me the opportunity to combine practical experience with exploring the potential of integrating technology in therapy for young children.

II. Current and Past Positions

- 2022 - Present: working in physiotherapy and speech therapy at Children's Hospital 2.

III. Awards and Honors

None

IV. Publications

None

V. Other projects and scholarships funded by VINIF

None

# I. PROPOSAL BUDGET

(Add/delete rows if necessary.)						Unit: Million VND

|  |  | Chi phí đơn vị |  |  |  |  | Tiền yêu cầu | Chia sẻ chi phí của người nộp đơn | Tổng |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Đơn vị |  | Số | Lượng | Tỉ lệ |  |  |  |
| A | Nhân lực |  | Tháng hoặc năm |  | tiền lương (tháng hoặc năm) | % công |  |  |  |
| A.1 | Senior Personnel |  |  |  |  |  |  |  | 2548.80 |
| A.1.1 | Nghiên cứu viên chính |  | Tháng | 30 | 40 | 30 | 360.00 |  | 360.00 |
| A.1.2 | Thành viên Chủ chốt 1 |  | months | 27 | 32 | 30 | 259.20 |  | 259.20 |
| A.1.3 | Thành viên Chủ chốt 2 |  | months | 27 | 32 | 30 | 259.20 |  | 259.20 |
| A.1.4 | Thành viên Chủ chốt 3 |  | months | 27 | 32 | 30 | 259.20 |  | 259.20 |
| A.1.5 | Thành viên Chủ chốt 4 |  | months | 30 | 32 | 30 | 288.00 |  | 288.00 |
| A.1.6 | Thành viên Chủ chốt 5 |  | months | 30 | 32 | 30 | 288.00 |  | 288.00 |
| A.1.7 | Thành viên Chủ chốt 6 |  | months | 30 | 32 | 30 | 288.00 |  | 288.00 |
| A.1.8 | Thành viên Chủ chốt 7 |  | months | 30 | 32 | 30 | 288.00 |  | 288.00 |
| A.1.9 | Thành viên Chủ chốt 8 |  | months | 27 | 32 | 30 | 259.20 |  | 259.20 |
| A.2 | Nhân lực khác |  |  |  |  |  |  |  | 576.00 |
| A.2.1 | Thành viên 1 |  | months | 24 | 16 | 30 | 115.20 |  | 115.20 |
| A.2.2 | Thành viên 2 |  | months | 24 | 16 | 30 | 115.20 |  | 115.20 |
| A.2.3 | Thành viên 3 |  | months | 24 | 16 | 30 | 115.20 |  | 115.20 |
| A.2.4 | Thành viên 4 |  | months | 24 | 16 | 30 | 115.20 |  | 115.20 |
| A.2.5 | Thành viên 5 |  | months | 24 | 16 | 30 | 115.20 |  | 115.20 |
| Tổng kinh phí nhân lực |  |  |  |  |  |  | 3124.80 | 0.00 | 3124.80 |
| B | Trang thiết bị |  |  | # đơn vị | giá mỗi hơn vị |  |  |  |  |
| B.1 | Google Cloud Computing (​​a2-highgpu-2g vCPUs: 24, RAM: 170 GiB, GPUs: 2) |  | months | 3 | 136.54 |  | 409.62 |  | 409.62 |
| Tổng kinh phí thiết bị |  |  |  |  |  |  | 409.62 | 0.00 | 409.62 |
| C | Đi lại |  | # người | # ngày | giá | % công |  |  |  |
| C.2 | Foreign |  |  |  |  |  |  |  |  |
| C.1.1 |  |  |  |  |  | 100% |  |  | 0.00 |
| C.2 | Domestic |  |  |  |  |  |  |  |  |
| C.2.1 |  |  |  |  |  | 100% |  |  | 0.00 |
| Tổng kinh phía đi lại |  |  |  |  |  |  | 0.00 | 0.00 | 0.00 |
| D | Chi phí trực tiếp khác |  |  |  |  |  |  |  |  |
| D.1 | Vật liệu và vật tư |  |  |  |  |  | 167.03 |  | 167.03 |
| D.2 | Chi phí xuất bản/ tài liệu |  |  |  |  |  | 550.00 |  | 550.00 |
| D.3 | Kinh phí thử nghiệm trên trẽ |  | trẻ | 50 | 3 |  | 150.00 |  | 150.00 |
| Tổng kinh phí trực tiếp khác |  |  |  |  |  |  | 867.03 | 0.00 | 867.03 |
| E | Tổng kinh phí trục tiếp |  |  |  |  |  | 4401.45 | 0.00 | 4401.45 |
| F | Chi phí không trực tiếp |  | (Tỷ lệ cụ thể và cơ sở) |  |  |  | 220.01 | 0.00 | 220.01 |
| F.1 | Chi phí quản lý |  | 5%, không vượt quá 300 triệu VND |  |  |  | 220.01 |  | 220.01 |
| G | Tổng chi phí dự án |  |  |  |  |  | 4621.46 | 0.00 | 4621.46 |

# BUDGET JUSTIFICATION

- Personnel labor

According to Circular 02/2023/TT-BKHCN issued by the Ministry of Science and Technology and Circular 03/2023/TT-BTC issued by the Ministry of Finance, the maximum funding for the Principal Investigator (PI) is 40 million VND per month. Funding for senior members and members is set at 80% and 40% of the PI's maximum funding, corresponding to 32 million VND/month and 16 million VND/month, respectively. According to VinIF program rules, each member must dedicate at least 30% of their working time to the project.

Quan Thanh Tho, Le Thanh Van, Ha Thi Thanh Huong, Ngo Thi Lua, and Huynh Kim Phat will participate throughout most of the project duration, except for the first six months of Phase 4, which will be dedicated to deploying the solution at Children’s Hospital 2. Therefore, their estimated participation is 30 person-months.

Pham Hoang Anh and Le Trong Nhan will mainly be involved in Phases 2, 3, and the final three months of Phase 4, as they are responsible for the hardware infrastructure required to deploy the solution. Their estimated participation is 27 person-months.

Trinh Huu Tung nad Nguyen Thanh Sang will be involved in Phases 1 and 4, with partial participation in Phases 2 and 3. Their estimated participation is 27 person-months.

Nguyen Quang Duc will primarily participate in Phases 2 and 3, with an estimated participation of 24 person-months.

Nguyen Chau Tuyet Nhu, Vu Nguyen Minh Duc, Nguyen Thi Dieu Linh, and Nguyen Ngoc Tuong Vy will be mainly involved in Phases 1 and 4, with partial participation in Phases 2 and 3. Their estimated participation is also 24 person-months.

- Equipment costs:

Based on our prior experience in training language models [73], an adequate GPU memory requirement for effective model training is approximately 160 GB of VRAM. The a2-highgpu-2g machine on Google Cloud meets this requirement, as it is equipped with 2×NVIDIA A100 80GB GPUs, 24 vCPUs, and 170 GiB of RAM. This machine is priced at approximately 5,364.14 USD per month under standard on-demand pricing. In addition to the computing configuration, we require a 256 GB bootable disk for storing the operating system, and 4×375 GB additional disk storage for saving trained models and datasets. These additional storage requirements bring the total monthly cost to approximately 5,508.74 USD. This estimate is based on Google's official pricing calculator (https://cloud.google.com/products/calculator).

According to the accounting exchange rate published by the Ministry of Finance in April 2025, where 1 USD = 24,786 VND, the monthly cost for Google Cloud computing translates to approximately 136.54 million VND.

This cloud server will primarily be used in Phase 2.4 (2 months) for training multimodal large language models, and Phase 3.1 (1 month) for testing and validating the entire pipeline. Hence, the estimated total duration of usage is three months, leading to a total projected cost of 409.62 million VND for Google Cloud computing services during the project.

- Other direct costs:

Materials and Supplies: We intend to build four AI Proxy devices, each is accompanied by a multidirectional microphone. Three of them will be put in the Children’s Hospital 2, Children’s Hospital 1, and City Children Hospital for deploying our solution, and we will keep one to research, develop, update, and fix bugs for future usage. The necessary hardware for a complete set is listed in the table below.

| No | Description | Unit | Quantity required | Unit price | Amount (VND) |
| --- | --- | --- | --- | --- | --- |
| 1 | NVIDIA Jetson Orin NX 16G Dev Kit (https://www.proe.vn/jetson-orin-nx-16g-dev-kit-us) | piece | 4 | 33.000.000 | 132.000.000 |
| 2 | Multidirectional Microphone + Speaker Jabra Speak2 75 MS/ UC (https://vinasound.vn/san-pham/loa-hoi-nghi-jabra-speak2-75) | piece | 4 | 7.890.000 | 31.560.000 |
| 3 | Box for NVIDIA Jetson (https://mlab.com.vn/vo-hop-metal-danh-cho-nvidia-jetson-orin-tich-hop-nut-nguon-anten-va-de-camera-doi-sp44-mlab-com-vn) | piece | 4 | 368.000 | 1.472.000 |
| 4 | Wires, cables, other necessary stuffs |  | 4 | 500.000 | 2.000.000 |
| Total |  |  |  |  | 167.032.000 |

Publication Costs: Based on the funding rates at Ho Chi Minh City University of Technology, we propose the following publication support costs:

- Top-tier publications (Q1 journals, A/A* conferences): 100,000,000 VND per paper

- Other publications (Scopus/ISI journals, other international conferences): 50,000,000 VND per paper

- Patents: 100,000,000 VND per patent

These proposed amounts are intended to cover publication fees, conference registration, travel expenses (if applicable), and other costs associated with the publication or patenting process.

Children's Experimental Costs: We intend to provide travel support for children participating in the implementation of our solution during Phase 4. Each child will receive a travel allowance of 500,000 VND per month for up to six months. As previously proposed, the experiment will involve 50 children.

# FACILITIES, EQUIPMENTS AND OTHER RESOURCES

At Ho Chi Minh City University of Technology - VNU-HCM, URA Lab led by Professor Quan Thanh Tho,  we already have small GPUs for testing and developing AI models. Moreover, the AC Lab directed by Professor Le Trong Nhan already has tools and equipment necessary to successfully build the hardware for the AI Proxy device in this proposal.

# SPECIAL INFORMATION AND SUPPLEMENTARY DOCUMENTATION

This project is a collaboration with Children’s Hospital 2 in Ho Chi Minh City. We have obtained a joint research agreement from Children’s Hospital 2, which is attached at the end of this document.

| VINGROUP INNOVATION FOUNDATION SCIENCE AND TECHNOLOGY RESEARCH GRANT | VINIF-A-TMDA Received. Reference code. (To be filled by VINIF). |
| --- | --- |

APPENDIX 01

List of Q1 journals and/ or rank A/A* conferences to be submitted:

| No. | Name of journal/conference | ISSN/ ISBN | Field |
| --- | --- | --- | --- |
| 1 | Nature | 1476-4687 | Multidisciplinary |
| 2 | Nature Machine Intelligence | 2522-5839 | Artificial Intelligence |
| 3 | Nature Neuroscience | 1546-1726 | Neuroscience |
| 4 | Nature Biotechnology | 1546-1696 | Biotechnology |
| 5 | Neural Information Processing Systems (NeurIPS) | Conference rank A* | Computer Science and Engineering |
| 6 | International Conference on Learning Representations (ICLR) | Conference rank A* | Computer Science and Engineering |
| 7 | International Conference on Machine Learning (ICML) | Conference rank A* | Computer Science and Engineering |
| 8 | Annual AAAI Conference on Artificial Intelligence (AAAI) | Conference rank A* | Artificial Intelligence |
| 9 | Annual Meeting of the Association for Computational Linguistics (ACL/NAACL/EACL) | Conference rank A/A* | Natural Language Processing |
| 10 | Empirical Methods in Natural Language Processing (EMNLP) | Conference rank A* | Natural Language Processing |

List of Q1 journals and/ or  rank A conferences to be submitted must be presented in Appendix 01.

NVIDIA Jetson Orin: https://www.nvidia.com/en-us/autonomous-machines/embedded-systems/jetson-orin