## SVI
| TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION (MONTH) | DURATION (MONTH) | PCT OF TASK COMPLETE | 2025 | [10 empty] | 2026
[8 empty] | 4 | 5 | 6 | 7 | 8 | 01/09-15/09 | 16/09-30/09 | 01/10-15/10 | 16/10-31/10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1 | Develop speech tasks
1.1 | Review literature on speech tasks, acoustic and linguistic features | Leon W | 2018-03-12 | 2018-03-15 | 3 | 2 | 100%
1.2 | Gather picture and text stimuli | Pete S | 2018-03-15 | 2018-03-21 | 6 | 2 | 90%
1.3 | Develop speech test for Vietnamese population | Steve L | 2018-03-16 | 2018-03-22 | 6 | 4 | 40%
1.4 | Rate by experts | Allen W | 2018-03-18 | 2018-03-22 | 4 | 4 | 70%
1.5 | First version of protocol |  |  |  |  | 1
1.6 | Doing pilot study |  |  |  |  | 2
1.7 | Assessing and re-build protocol |  |  |  |  | 1
1.8 | Write test script | Malik M | 2018-03-19 | 2018-03-22 | 3 | 1 | 60%
2 | Collect data
2.1 | Submit the description of the science and technology for Military Hospital 175 for research ethics approval | Steve L | 2018-03-24 | 2018-03-28 | 4 | 4 | 22%
2.2 | Recuit participant from hospital | Allen W | 2018-03-29 | 2018-04-02 | 3 | 6 | 16% | bar: 11 to 2026 3
2.3 | Clinical psychiasists assess participants | Malik M |  |  | 0 | 6 | 0% | bar: 11 to 2026 3
2.4 | Conduct developed speech test and record participant's performance | Malik M |  |  | 0 | 6 | 0% | bar: 11 to 2026 3
2.5 | Extract linguistic and acoustic features on recording |  |  |  |  | 2 | bar: 2026 4 to 2026 5
2.6 | Statistical analysis to validate the acoustic and linguistic features in differentiating AD and MCI. |  |  |  |  | 1 | bar: 2026 6
2.7 | Write the manuscript |  |  |  |  | 1 | bar: 2026 7 to 2026 9
3 | Project Launch & Execution
3.1 | Status & Tracking | Pete S |  |  | 0 |  | 0%
3.2 | KPIs | Leon W |  |  | 0 |  | 0%
3.2.1 | Monitoring | Kylie R |  |  | 0 |  | 0%
3.2.2 | Forecasts | Kylie R |  |  | 0 |  | 0%
3.3 | Project Updates | Pete S |  |  | 0 |  | 0%
3.3.1 | Chart Updates | Malik M |  |  | 0 |  | 0%
4 | Project Performance/Monitoring
4.1 | Project Objectives | Steve L |  |  | 0 |  | 0%
4.2 | Quality Deliverables | Allen W |  |  | 0 |  | 0%
4.3 | Effort & Cost Tracking | Malik M |  |  | 0 |  | 0%
4.4 | Project Performance | Malik M |  |  | 0 |  | 0%

## Terumo
| TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION (MONTH) | DURATION (MONTH) | PCT OF TASK COMPLETE | 2025 |  |  |  | 2026 | [11 empty] | 2027
[8 empty] | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 8 | 9
1 | Building protocol and check feasibility of protocol.
1.1 | Protocol finalization and ethics approval | Leon W | 2018-03-12 | 2018-03-15 | 3 | 2 | 100% | bar: 2025 9 to 2025 12
1.2 | Pilot study execution | Pete S | 2018-03-15 | 2018-03-21 | 6 | 2 | 90% | bar: 2026 1
1.3 | Develop speech test for Vietnamese population | Steve L | 2018-03-16 | 2018-03-22 | 6 | 4 | 40% | bar: 2025 10 to 2026 1
1.4 | Rate by experts | Allen W | 2018-03-18 | 2018-03-22 | 4 | 4 | 70% | bar: 2025 10 to 2026 1
1.5 | First version of protocol |  |  |  |  | 1 | bar: 2026 1
1.6 | Doing pilot study |  |  |  |  | 2 | bar: 2026 2
1.7 | Assessing and re-build protocol |  |  |  |  | 1 | bar: 2026 3 to 2026 4
1.8 | Write test script | Malik M | 2018-03-19 | 2018-03-22 | 3 | 1 | 60%
2 | Main collection.
2.1 | Participant Recruitment and Clinical Assessment | Steve L | 2018-03-24 | 2018-03-28 | 4 | 4 | 22%
2.2 | Speech Data Collection | Allen W | 2018-03-29 | 2018-04-02 | 3 | 6 | 16%
2.3 | Feature Extraction and Analysis | Malik M |  |  | 0 | 6 | 0% | bar: 2026 9 to 2026 10
2.4 | Results analysis, writing report dissemination | Malik M |  |  | 0 | 6 | 0% | bar: 2026 11 to 2027 2
2.5 | Extract linguistic and acoustic features on recording |  |  |  |  | 2 | bar: 2026 11 to 2026 12
2.6 | Statistical analysis to validate the acoustic and linguistic features in differentiating AD and MCI. |  |  |  |  | 1 | bar: 2027 1
2.7 | Write the manuscript |  |  |  |  | 1 | bar: 2027 2 to 2027 9
3 | Project Launch & Execution
3.1 | Status & Tracking | Pete S |  |  | 0 |  | 0%
3.2 | KPIs | Leon W |  |  | 0 |  | 0%
3.2.1 | Monitoring | Kylie R |  |  | 0 |  | 0%
3.2.2 | Forecasts | Kylie R |  |  | 0 |  | 0%
3.3 | Project Updates | Pete S |  |  | 0 |  | 0%
3.3.1 | Chart Updates | Malik M |  |  | 0 |  | 0%
4 | Project Performance/Monitoring
4.1 | Project Objectives | Steve L |  |  | 0 |  | 0%
4.2 | Quality Deliverables | Allen W |  |  | 0 |  | 0%
4.3 | Effort & Cost Tracking | Malik M |  |  | 0 |  | 0%
4.4 | Project Performance | Malik M |  |  | 0 |  | 0%